Early Implementation of AHP Career Framework using The Calderdale Framework

Final Report

Produced For Skills for Health

Produced by

Rachael Smith and Jayne Duffy

Calderdale Framework Project Leads

Calderdale & Huddersfield NHS Foundation Trust

December 2009

EARLY IMPLEMENTER PROJECT: SKILLS FOR HEALTH AHP CAREER FRAMEWORK

CONTENTS

- Executive summary

- Introduction: National Context

- About this Project

- Benefits Realisation

- The Calderdale Framework

- Local Context

- Implementation – The Seven Stages:

1. Awareness Raising

2. Service Analysis

3. Task Analysis

4. Competency Mapping/Generation

5. Supporting Systems

6. Training

7. Sustaining

- Levelling to AHP Career Framework

- Governance of Project

- Consultation Events

- Outcomes

- Added Benefits

- Recommendations

- Appendices

- References

National Context

The UK has a skills shortage and its demographics indicate that there are fewer people of working age; the reality of this is that by 2016 70% of the current NHS workforce will either have retired or need up skilling to meet demand. The NHS needs to invest in the skill base of staff to grow local workforces and thus to become the “employer of choice” . In order to improve employability and retain staff in the NHS as a whole, competence based transferable skills are required . The NHS of the future aims to deliver quality, person centered services delivered by multi-skilled staff .

The skills sector agreement for health  aims to raise the quality of health and healthcare by creating a skilled and flexible workforce through nationally recognised competences (National Occupational Standards). In view of the skills shortage, there is a need to realise the potential and increase the productivity of the NHS workforce. For new and extended roles the NHS needs a competence based workforce as opposed to one that relies on traditional roles. There is a national drive to encourage  professional staff to broaden or add to their scope of practice . In the future, jobs ‘will be defined by competences rather than separated by profession’ and there will be a flattening in the current demand for professionally qualified staff . Service managers should “design services to meet public and patient needs rather than start with the assumption that particular professions are required” because professional groups have areas of common and shared competencies . The NHS needs to extend multi-professional roles .

With the shift from hospital based care to care closer to home the DH  requires a more flexible workforce in the health and social care system that is responsive to changing demand. Staff need the skills and knowledge to deliver high quality, safe care in new clinical settings and closer to home .

New roles and skill mix will ensure concordance across professional groups when the same competence applies. The training and education of health staff needs to adapt to improve the quality of care for patients, support workers need to be “appropriately trained” . “A competence based approach to designing the workforce is required to ensure that the right skills are available at the right time and delivered in the right place” . New legislation on the regulation of the health and social care workforce requires evidence that staff are competent to carry out their duties .

There is a need for a competence based career framework for Allied Health Professionals and support workers to enable teams to be built around patient needs, linked to national occupational standards to ensure clinical quality . National occupational standards provide the detailed framework necessary to measure support worker performance in order to create a competent, well qualified workforce able to meet the needs of the public. In addition to this, a skills escalation strategy for support staff will create opportunities for career development  .  A key new role is seen as that of Assistant Practitioner who ‘would be able to deliver elements of health & social care and undertake clinical work in domains that have previously only been in the remit of registered professionals. The Assistant Practitioner may transcend professional boundaries’. (Skills for Health 2009)

A Career Framework for AHP staff has been developed by Skills for Health (SfH) and the Chief Health Professions Officers for the 4 nations. The framework comprises of National Workforce Competences (National Occupational Standards, NOS). These NOS provide learners with transferable competences linked to the Knowledge and Skills Framework . This is a starting point for a more flexible workforce, and new roles.

ABOUT THIS PROJECT

Skills for Health (SfH) is the Sector Skills Council for health (SSC). Its strategic intent is to help develop a skilled, flexible and productive workforce for the whole health sector in all UK nations in order to raise the quality of health and healthcare for the public, patients and service users. Over the past two years Skills for Health has been sponsored by the Department of Health to develop a competence based career framework for Allied Health Professionals. The framework has been designed to reflect all functions at all levels and grades of staff across the AHPs.

Since 2001 the Clinical Therapy & Rehabilitation Directorate of Calderdale and Huddersfield NHS Foundation Trust have been working on a functional decision making model which provides a clear and systematic method for analysing services and managing delegation to support staff. Skill mix review is inherent in the process, leading to effective & efficient use of staff. Once implemented it leads to the identification & development of task related competencies which provide a comprehensive and robust training package for the support worker and ensure patients receive consistent, evidence based interventions. This model also helps derive appropriate tasks for skills sharing across professional boundaries (blurred boundary competencies). The Calderdale Framework has developed into a transformational tool to support new ways of working.

It was agreed that Calderdale & Huddersfield NHS Foundation Trust would become an early implementer for the Modernising AHP Career Framework. This would bring together the work previously done with the Calderdale Framework and the recommendations of the Darzi review to inform service development.

The project purpose was to meet Skills for Health’s strategic intent to:

- Support the development of innovative, patient and user focussed service redesign and new ways of working, including the use of existing, extended and new roles within modernised healthcare careers.

- Promote the use of competence based approaches to planning and development through the production of frameworks, products, tools and guides which have an excellent reputation for quality and ease of use.

- Demonstrate the benefits to the public, patients, service users and employers of a competence based approach to developing a more skilled, flexible and productive workforce.

- Identify possible innovative education, training & development solutions to reduce skills gaps.

- Champion the development of innovative education, training and development solutions, including e-learning.

Funding was provided by Skills for Health to secure dedicated support of the developers of The Calderdale Framework as Project Leads (1.73 wte), and 0.2 wte of admin support. The project was managed using Prince 2 methodology, to ensure appropriate governance and progress.

The main aims of the project were to use the Calderdale Framework to:

- Demonstrate the strategic application of the National Career Framework

- Review Skill Mix with a focus on modernised service models in 2 Teams: MacMillan Cancer rehabilitation Team and Early Orthopaedic Discharge team.

- Explore the development of a level 4 Rehabilitation Assistant Practitioner in the above teams.

- Explore the therapy roles at career frameworks levels 6 & 7 in terms of shared skills in the above teams.

Benefits Realisation

Benefits realisation not only identifies whether the objectives have been achieved but also identifies the benefit of achieving these objectives. This is the ‘so what’ factor as opposed to ticking the box as ‘achieved’. Undertaking a benefits realisation analysis clarified the purpose and intent of the project, to ensure it produced outcomes of value to the wider health & social care economy. This process was facilitated by experts from Skills for Health.

There were 4 objectives/products to be achieved:

- to define the team competencies and profile based on patient needs for the 2 teams

- To identify generic competencies to be used in an MDT (and identify competencies that remain within a specialised profession)

- To develop a NOS cluster for new roles at Level 4

- To identify the educational requirements needed to underpin these new ways of working.

Final outcomes and benefits were then identified for the above objectives. Table 1 shows these agreed benefits realisation for this project.

Table 1.  Skills for Health Early Implementer Project: Calderdale Framework Benefits Realisation

THE CALDERDALE FRAMEWORK

The Calderdale Framework was developed in response to patient need and was originally based on the theories of Saunders (1996).

In 2001 the Calderdale & the Huddersfield Acute NHS Trusts merged. In 2005 the Clinical Therapy & Rehabilitation Directorate (CT & R) was formed hosting all the therapy and rehabilitation staff in the Trust.  As a means of ensuring all services were delivering agreed best practice the Clinical Director agreed to implement the Calderdale Framework (CF) which had been developed within the Calderdale Community Rehabilitation Teams, then referred to as the Functional Model of Delegation (NHS Modernisation Agency 2004, pages 27-28) across the whole of Clinical Therapies and Rehabilitation Directorate (Smith & Duffy in press).

# The Calderdale Framework (Smith & Duffy 2008) comprises 7 stages, each of which empowers clinicians to take ownership of the process. (see fig 1)

# Figure1. The Calderdale Framework

LOCAL CONTEXT

Following the formation of Calderdale & Huddersfield Foundation NHS Trust(CHFT), surgical services were reconfigured, so that services were delivered from one or other site (and not both).One of the major changes was to the Orthopaedic service namely that all elective surgery would be delivered from the Calderdale site and all the trauma services from the Huddersfield site. Within the CT&R Directorate one of the services most affected by this was the long established early orthopaedic discharge service known as ‘Rehabilitation at Home Team’. This team supported the early discharge of patients who had undergone elective orthopaedic surgery (mainly hip or knee replacement), by providing post operative rehabilitation in the patient’s home.

CHFT was successful in gaining funding from MacMillan in 2008 for a community based Cancer Rehabilitation Team. This team was commissioned in response to patient need as identified in the Cancer Reform Strategy (2007), in particular to ‘improve the experience of people living with and beyond cancer’ and ‘ensuring care is delivered in the most appropriate setting’. Patients with a diagnosis of cancer are living longer and more people are surviving cancer, leading to an increased need for rehabilitation in order to maximise their quality of life. The MacMillan Rehabilitation Team operates across the whole of CHFT catchment area, providing rehabilitation to patients in a variety of community settings.

These two teams were selected for the project as each of them had scope to review their skill mix. The MacMillan team because it was new and had already identified the need for a higher level assistant worker, and the Rehabilitation at Home team because it faced changes due to restructuring and was effectively merging two teams into one.

1. MacMillan Team

At the start of the project in October 2008 this team comprised:

Team Leader                     AfC Band 7

Occupational Therapist     AfC Band 6

Physiotherapist                 AfC Band 6

Rehabilitation Assistant    AfC Band 3 (x 2)

It was recognised early in the project (following service analysis & task analysis) that the team needed an Assistant Practitioner. The issues to clarify were:

- What did this role involve

- What was their scope of practice

- What competences and local competencies did they need

- What underpinning knowledge did they need

- How was this going to be addressed

The team also recognised that in order to deliver effective, patient centred care there was a need to share skills across the professional boundaries of Occupational & Physiotherapy.

2. Rehabilitation at Home Team

At the start of the project in October 2008 this team comprised:

Team Leader                       AfC Band 7

Occpational Therapist         AfC Band 7

Physiotherapist                   AfC Band 7(x2)

Physiotherapist                   AfC Band 6

Nurse                                  AfC Band 6

Rehabilitation Assistants    AfC Band 3 (x8)

Elective orthopaedic throughput had increased with the 18 week initiative, increasing demand along with ‘choose and book’. This increase in workload provided the scope to explore the opportunity of an Assistant Practitioner role, in conjunction with reviewing skill mix and skill sets of all team members.

IMPLEMENTATION: THE SEVEN STAGES

- Awareness Raising (focus on staff engagement)

This stage is vital to ensure managers and clinical staff are fully informed and aware of the process and benefits of the Calderdale Framework.

This stage also included information sharing about the Early Implementer Project and Skills for Health, which was very positively received by the teams.

Awareness raising was carried out with the MacMillan Rehabilitation team first as they were  new and still developing, and the project had identified benefits of linking to another National Cancer Project (Cancer Pathways).

The Rehabilitation at Home team were already familiar with the Calderdale Framework and so the awareness raising with them was largely about the early Implementer Project & Skills for Health.

Awareness raising was carried out in November 2008 with each team over a working lunch, with time built in to allow individuals to ask questions and become involved. ‘Champions’ were identified at this stage,  who were keen to be involved and who took responsibility for keeping the process moving within their team. They were given additional training to enable them to do this.

The Rehabilitation at Home team had 2 Champions who had been involved with the Calderdale Framework previously.

The MacMillan team took the view that as they had such a small team they were all in effect Champions as all would become involved.

- Service Analysis (Focus on potential to change)

This is a crucial stage which requires front line staff to identify the purpose and all the functions of their service. They must also consider who currently undertakes these and question whether patient need is being met. Service functions are then broken down into tasks which are broken further into smaller & smaller subtasks, and importantly who does these currently is noted. At this point, potential service changes which would improve efficiency and patient experience can be suggested and explored. This process is facilitated and lasts for around ½ day, with as many staff from the team as possible being involved. Service Analysis provides clinical staff with ‘time out’ from the front line to reflect on whether their skills are being utilised to best effect and encourages a solution focussed dialogue.

Each team had a ½ day facilitated session which highlighted where there was duplication and specialisation of interventions.

For the MacMillan team this session catalysed the notion that an Assistant Practitioner could improve their service. However for both teams it was apparent that although skill sharing took place and there was a willingness to develop this, training to support this was not robust. Clinicians expressed concern over their ability to demonstrate competence when undertaking tasks traditionally outside the scope of their practice.

Service Analysis took place between January & February 2009.

Baseline data was gathered at this stage of the project.

3. Task Analysis (Focus on Risk Management)

This stage involves front line clinical staff and clinical leads analysing the subtasks for suitability to delegate and /or skill share, based on whether and how the risks of doing so are manageable. A decision table consisting of ten questions is used to facilitate open & objective discussion regarding the potential risks of allowing that task to be done by another person. The clinical group come to a consensus as to whether these risks can be managed along with possible solutions for managing them. Part of this process also involves considering the cost vs. benefit of training another person to undertake a given task. Tasks requiring an in depth knowledge require a greater training input and can therefore be more costly. These are typically tasks involving clinical reasoning (such as assessment, diagnosis, treatment planning). However these tasks can be delegated or shared with the development of suitable protocols alongside some additional training. Where this is the case an Assistant Practitioner role is appropriate (for this role suitable tasks & cases are allocated rather than delegated). The frequency with which a given task is carried out is also an important consideration here, as ‘high volume’ tasks are more cost beneficial to delegate/allocate or share in terms of training and retention of competence.

The RAH team already had a competence based training pack for delegation to Rehabilitation Assistants, derived from the original work in the Directorate. This negated the need to task analyse the whole cohort of tasks identified from service analysis. In conjunction with this earlier work we were able to produce a competency based training pack for delegation for the MacMillan Team Rehabilitation Assistants by a process of mapping from their service analysis to the existing competency directory.

For the MacMillan Rehabilitation Team task analysis took 2 days overall. This was due to:

- the complexity of some of the tasks,

- the specific caseload

- the identification of tasks suitable for an Assistant Practitioner and skill sharing.

For the RAH team this stage took 1 day focussing heavily on skill sharing around assessment and the potential for an Assistant Practitioner role.

The result of this stage was the production of three cohorts of clinical

tasks, i.e. those suitable for:

- Skill sharing across qualified Practitioners

- Allocation to  an Assistant Practitioner

- Delegation to a Rehabilitation Assistant

4. Competency Generation/Mapping to NOS (Focus on Quality)

Having agreed on the tasks to delegate, allocate and share the next stage was for clinicians to agree on how these should be performed. This involved them agreeing best practice, based on evidence, where available, or peer consensus. Tasks were then written into local competencies i.e. in a format which explicitly laid out how each task was to be performed (behavioural and functional elements). For the purpose of this project the definition of  competencies  is ‘the skills demonstrated to meet the requirements of a specific task’. In essence performance = competence in action. In this context the local competencies provide a detailed training document as well as a record of an individual’s ability to undertake the tasks.

For this project these tasks also provided the focus for searching the Skills for Health National Occupational Standard (NOS) database. These NOS provided broad consensus of best practice across all the functions within a job description and not just the clinical elements. The local competencies derived from this process contextualised and evidenced the clinical NOS (see table 2 for example).

The NOS search was undertaken by the Project Leads following training from Skills for Health. This was done using job description statements as well as tasks from task analysis, and required a detailed clinical understanding of the services involved. These job descriptions were then submitted to Skills for Health for levelling of each role against the AHP career framework (see appendix).

| Job Description Statement | Skills for Health Competences (National Occupational Standards) | Local Competencies |
| --- | --- | --- |
| ‘Plans & implements individual assessments & treatments for patients’ | CHS137: Implement mobility & movement programmes …. | Protocol based assessment for mobility & walking aid provision |

Table 2 Example of Mapping Job description to NOS & Local Competency

- Supporting Systems (Focus on Governance)

This step ensures that systems within the workplace are set up to enable the management of the risks associated with new ways of working.

At an organisational level this means setting up clinical supervision & reflective practice for all staff. This ensures an explicit understanding of scope of practice for each role within the service, and provides quality assurance, risk management and on going staff development.

At a team level it is vital to ensure communication networks are clear & robust. All staff need to know what they should feedback, when to feedback and in what way. Also they must know when to stop a given task. In the case of delegated work it is expected that any deviation from the plan is fed back to the qualified Practitioner. In the case of allocated work or skill sharing, staff should seek advice and support if the task is going beyond the protocol. An example of underpinning supporting systems is set out in table 3 below. As part of the project, both teams have implemented the systems as listed.

| Checklist | Tick and Date when completed |
| --- | --- |
| Team Register |  |
| Caseload allocation systems in place e.g. screening tool |  |
| When to stop task: local competency written |  |
| All team members training to include above (qualified and non qualified) |  |
| Frequency of routine feedback established |  |
| Key issues to feedback established (outside of routine issues) |  |
| Means of feedback established and all staff aware of these |  |
| Contingency plan established if a staff member is not available to receive feedback |  |
| Care plans are explicit about who does what |  |
| System of clinical supervision established (for qualified and non qualified staff) |  |
| System of reflective practice established (for qualified and non qualified staff) |  |

Table 3 Supporting Systems Checklist

- Training (Focus on Staff Development).

This is facilitated by appropriate training of all staff.  Qualified staff are not taught about delegation as undergraduates and delegation skills are picked up once working which leads to the variation in practice observed. All qualified staff need training to ensure they understand how the competences have been derived and what the support staff are competent to do.

Support staff need to be trained so they are competent. This must be done

as per the competency by occupationally competent staff. All staff need

training to understand the communication systems regarding what,

when & how to feedback and when a task is to be halted. Work based

training for tasks appropriate for Assistant Practitioners and skill sharing

was identified (see appendix).

Within this project a key outcome was to identify the educational needs for

the Assistant Practitioner role, and for skill sharing across qualified

Practitioners. The educational partners involved were University of

Bradford (Assistant Practitioner Role) and University of Huddersfield

(Interdisciplinary Roles).

University of Bradford

Contact: Jane Priestley, 	Senior Lecturer/University Teaching Fellow

Division of Rehabilitation Studies

University of Bradford (01274) 236585

Time Line

Noted below are the key events towards the development of the learning package for the new level 4 roles (Assistant Practitioner), the detail of which is shown in the Appendix. At the outset of the project the intention was the identification of educational needs for this role, whereas the outcome has surpassed this, with the development of the bespoke Certificate in Reablement.  During the meetings with the University it became apparent that a Certificate in Reablement would allow wider participation across Health and Social Care, thereby maximising flexibility of the workforce. The award recognises and accredits work based learning, and so tailors the content to the learner and service. This is an example of a ‘Shell Award’.

- April 2011:  First cohort expected to complete Certificate.

- April 2010 : Certificate in Reablement (120 credits) – first cohort

- February 2010: Final Approval Event

- November 2009 : Phase 1  Approval attained

- October/November 2009: APEL process initiated with external consultant in conjunction with CHFT training department.

- October 2009: Consultation event at University of Bradford with key stakeholders

- September 2009: Phase 1 Approval sought.

- August 2009: feasibility meeting with CHFT training department.

- June 2009: Phase 1 Approval tabled

- May 2009: scoping of proposal initiated.

- May 2009: Consultation event with Rehabilitation Assistants

- March 2009: meeting with CT & R Clinical Director, SHA & University to establish the need for this development.

- March 2009: Jane Priestley joined the Project Steering group.

- February 2009: Project Leads introduced to WYLLN and ESCALATE

- January 2009: Project Leads initiate meeting with Jane Priestley

(Minutes are available for all of the above)

University of Huddersfield

Contact: Sara Eastburn, Head of Division of Rehabilitation

School of Human & Health Science

University of Huddersfield (01484) 472911

Time Line

Noted below are key events in the development of post graduate, interdisciplinary learning. At this stage formal accreditation has not been included, as the study days will provide a pilot on which to base further work.

The study days have been based on consultation with qualified clinicians, the details of which can be found in the appendix.

- Jan/Feb 2010: Post Graduate study days in:

- The basis of clinical exercise prescription

- The issuing of basic equipment

- Modules of Cancer Rehabilitation (Masters level)

- November 2009:agreed content & format of delivery

- October 2009:feedback to University service constraints of proposal

- September 2009:University proposal circulated to clinicians

- April 2009: report submitted to CHFT

- March 2009: shadowing exercise undertaken by University

- February 2009: staff consultation event between University and clinicians.

- January 2009: Project Leads attended meeting with Sara Eastburn

- December 2008: Project Leads linked to University of Huddersfield

(Minutes/notes are available for all the above)

Using the Calderdale Framework, employers and education institutions are able to truly work in partnership to develop education packages.This approach follows SfH learning design principles of facilitating employers to describe the education and training needs to deliver current and future services and of current and future employees.

- Sustaining  (Focus on Embedding & Monitoring)

The Calderdale Framework has become part of organisational and team induction to ensure that all staff (new starters and rotational staff) understand and are trained in their role. This is under pinned within the Trusts PDR system and links with KSF.

Within the Directorate there is a protocol for the development of new competencies, along with standards for delegation.

An outcome of the project in terms of sustaining will be the exploration of competency based job descriptions (see appendix 2).

LEVELLING TO AHP CAREER FRAMEWORK

Skills for Health have developed a tool to allow jobs to be ascribed a level on the Career Framework. This involves the use of an algorithm that gives weighting to elements of a job. The Career Framework for Health provides guidance for NHS and partner organisations on the implementation of the flexible career and skills escalator concept, enabling an individual member of staff with transferable competency based skills to progress in a direction which meets workforce service and individual need

The main thrust of the Career Framework is that it identifies role responsibility rather than a particular pay band which gives a consistency of language across national arena but with flexibility for local health organisations.

At this stage this tool is not available to employers, so roles within this project were levelled by Skills for Health staff.

The levelling tool consists of eight descriptors which have been extensively tested, and are organised into eight domains. The domains have nine levels with a series of statements which define the level within that domain. The Career Framework tool aggregates these domain levels to provide a single level - this is the Career Framework level.

Job descriptions for roles already established in the two teams were used, and where new roles were identified new job descriptions were written to reflect the skills and responsibilities of those roles.

It was evident that understanding the context of some of the roles was needed to accurately level them. This was an issue with the band 3 role, the team coordinator role and the clinical lead role. In part this was due to the wording of the job descriptions, in that they that did not always fully articulate the detail of the role in context, which impacted on the levelling process. The result was that initially the band 3 role came out as a level 4 role, although clinically this was a level 3 role. The clinical lead and team leader roles were initially levelled to Career Framework level 6.  This has lead to the directorate revisiting band 3 and band 4 job descriptions, and an opportunity to further explore skill mix.

Appendix 3 gives an illustration of the rational for the levelling of the MacMillan Assistant Practitioner role.

GOVERNANCE OF THE PROJECT

The project followed Prince 2 methodology and therefore had the following governance structure:

Project Board:

This met every 4 months see below for its membership:

| NAME | ORGANISATION | POSITION |
| --- | --- | --- |
| Alison Strode | Skills for Health | Divisional Manager |
| Joanna Birch | CHFT | Clinical Director |
| Monica Slocombe | CHFT | Therapy services Manager |
| Rachael Smith | CHFT | Project Lead |
| Jayne Duffy | CHFT | Project Lead |

Project Steering Group

This met every 8 weeks, where the group was updated on progress and issues arising were tabled. See below for membership of this group

| NAME | ORGANISATION | POSITION |
| --- | --- | --- |
| Joanna Birch | CHFT | Clinical Director |
| Chris Lamb | Skills for Health | Project Manager |
| Gael Stephenson | Skills for Health | Project Support |
| Rachael Smith | CHFT | Project Lead |
| Jayne Duffy | CHFT | Project Lead |
| Monica Slocombe | CHFT | Therapy services Manager |
| Judy Lennon | CHFT | Paediatric Services Manager (Governance Rep) |
| Lorraine Kershaw | CHFT | Team Coordinator (Rehab Rep) |
| Allan Hough | CHFT | Rehabilitation Assistant |
| Jane Priestley | Bradford University | Senior Lecturer |
| Sara Eastburn | Huddersfield University | Head of Division (Rehab) |

Project Reference Group

This met every 3 months and was a valuable source of moderation and constructive advice for the products of the project. It helped ensure that what came out of the project met stakeholder’s needs. The membership of this group is shown in the table below:

| NAME | ORGANISATION | POSITION |
| --- | --- | --- |
| Joanna Birch | CHFT | Clinical Director (Chair) |
| Jayne Duffy | CHFT | Project Lead |
| Rachael Smith | CHFT | Project Lead |
| Nicola Byrne | CHFT | MacMillan Rehab Team Leader |
| Joanne Vaughan | CHFT | RAH Team Leader |
| Elizabeth Foley | SHA | AHP Lead |
| Alison Ackew | SHA |  |
| Jackie Turnpenney | Cancer Action Team | NW Region Lead |
| Lorraine MacDonald | MacMillan | MacMillan development Coordinator |
| Janet Cawtheray | Calderdale PCT | Cancer services Commissioner |
| Claire Wilson | CHFT | Assistant Director Personnel & Development |
| Pauline Pilcher | CHFT | Union Convenor |

The milestones for the project were set out on a GANTT chart (see figure 1)

Figure 1 Project Gantt chart

CONSULTATION EVENTS

Throughout the project various stakeholders have been consulted with, detail of each consultation can be found in Appendix 8.

Key consultation events are listed below:

Time Line

- October 2009: University of Bradford hosted an event for NHS, Social Care, SHA, Skills for Health, Skills for Care, professional Bodies re proposed Certificate in Reablement.

- September/October 2009: 1to 1 interview with patient re impact of project.

- September 2009: CHFT Membership Council Board consulted re potential impact of project & new ways of working.

- May 2009: Support staff at CHFT & Calderdale PCT consulted re education needs.

- March 2009: University of Huddersfield shadowed & consulted with qualified staff re post grad education needs/opportunities.

- February 2009: Qualified staff consulted re post grad education needs.

These were undertaken to ensure the outputs of the project had value, not only to the patients and staff of CHFT but the local and extended health economy.

OUTCOMES

All outcomes as set out in the Benefits Realisation table have been met:

- Competency based job descriptions levelled to the AHP Career Framework.

- Two new level 4 posts being advertised in Rehabilitation at Home team.

- Level 4 role to be operational in the MacMillan Rehabilitation Team from January 2010.

- Competency training packs for level 3, level 4 and level 6/7 roles have been developed.

- Linking with the National Cancer Network on implementation of cancer Pathways and the implications of competency based roles on indicative staffing.

- Competence clusters developed for level 4 roles in both teams.

- Certificate in Reablement phase 1 approval at University of Bradford (see appendix for course design).

- Interdisciplinary training events planned at University of Huddersfield

The benefit evidence will be collected throughout 2010.

ADDED BENEFITS

The project has lead to several additional outputs which were not identified at the outset. These are listed below:

- Nationally Transferable Role (NTR).

Skills for Health are in the process of developing a database of Nationally Transferable Roles, which identify NOS and indicative educational requirements for Assistant Practitioner and Advanced Practitioner as part of the 18 week pathway. The Assistant Practitioner role (level 4) within RAH has been accepted as an example of one of these NTR on the Orthopaedic 18 week pathway.

- Links to West Yorkshire Lifelong Learning Network(WYLLN) & Escalate

Escalate is part of the University of Bradford, and was specifically developed to address work based learning needs, in conjunction with recognising existing work based learning.  The project has enabled CHFT to become involved with the development of ‘Shell Awards’ at all levels.

3. Yorkshire & the Humber SHA

As a result of the consultation events links have been made with our local SHA to explore the value of spreading this work across the region.

RECOMMENDATIONS

As an early implementer of the AHP Career Framework we recommend   the use of The Calderdale Framework as a transformational tool to identify new ways of working, with the resulting clarification of roles, responsibilities and development needs which can then be levelled against the AHP Career Framework. The Calderdale Framework ensures that a process with objectivity and rigour is followed, thereby quality assuring the outcome for patients, staff and commissioners.

,

In order to implement the AHP Career Framework we would recommend

a ‘train the trainer’ approach is taken. This would involve developing a

quality assured training programme which would allow consistent

application of The Calderdale Framework and Skills for Health tools. This

would not only facilitate new roles but also progression between them.

The development of NTR’s which link to the AHP Career Framework

would greatly ease its implementation, given the time constraints and skill

required to search for appropriate NOS. As previously stated we

recommend the use of The Calderdale Framework to support the

identification and need for these new roles, otherwise uptake may be

limited.

The process of levelling a role to The Career Framework is

based on the Job description. It is important therefore to ensure that the

current job description for a given role accurately reflects the skill set and

responsibility that the given role requires.

Future work needs to investigate the development of staff at levels 7 and

above, exploring opportunities to extend scope across disciplines,

interface with medical roles and the development of new

clinical/diagnostic roles, resulting in AHP led services. There needs to be

dialogue between professional and registering bodies in order to

accommodate these new workers.

Further work needs to be undertaken within service and HEI’s to maximise

the capability of the AHP workforce in a flexible & responsive manner.

This could also contribute to the debate over registration of support

workers and specifically the Assistant Practitioners.

The evaluation of identified benefits should continue for the next 12 – 18 months to measure the impact of the changes. This information will be shared with Skills for Health.

APPENDICES

- Project Implementation Document (PID)

- Competency based Job Description (example)

- Levelling to AHP Career Framework

- Example of a Nationally Transferable Role

- Index of local competencies (Level 3, level 4, level 6/7)

- Certificate in Reablement

- Post Graduate Study Days to support Blurred Boundary working

- Consultation Event notes

APPENDIX 1 – PID

Skills for Health/Calderdale and Huddersfield NHS Foundation Trust.

Joint Project Outline Specification

1.	Purpose of this document

The purpose of this document is to describe a proposed joint project between the Calderdale and Huddersfield NHS Foundation Trust and Skills for Health (SfH) in sufficient detail so that it can be signed off by the relevant sponsors and initiated. The Specification will cover the following:

- Background to the project

- Project purpose, main aims scope

- Sub projects and general timescales (each sub-project will have its own project plan)

- Project controls and management arrangements

- Initial project resources

- Quality Assurance arrangements

- Dependencies and linkages

- Initial Risk Log

2.	Background to the project

SfH is the health Sector Skills Council (SSC). Its strategic intent is to help develop a skilled, flexible and productive workforce for the whole health sector in all UK nations to raise the quality of health and healthcare for the public, patients and service users.

- Engaging with health sector employers to ensure an authoritative sector voice on skills and workforce development

- Informing the development and application of whole sector workforce policies through research, evaluation and the provision of robust labour market intelligence

- Helping to develop and implement solutions which deliver a skilled, flexible and modernised workforce capable of improving productivity, performance and reducing health inequalities

- Championing and demonstrating the benefits of an approach to workforce planning and development that is based on the common currency of national workforce competences.

Over the past two years Skills for Health has been sponsored by the Department of Health to develop a competence based career framework for Allied Health Professionals. The framework has been designed to reflect all functions at all levels and grades of staff across the AHPs.

Since 2001 Calderdale and Huddersfield NHS Foundation Trust have been working on functional decision making model which provides a clear and systematic method for analysing & transforming services and managing delegation to support staff with skill mix review being inherent in the process. Once implemented it leads to the identification & development of task related competences which provide a comprehensive and robust training package for the support worker and ensure patients receive consistent, evidence based interventions. This model also helps derive appropriate tasks for skills sharing across professional (blurred boundary competences).

On 1st May 2008 a meeting was held to discuss the prospect of being an early implementer for the Modernising AHP careers. This would bring together the work previously done at Calderdale and Huddersfield NHS Foundation trust and the recommendations of the Darzi review to inform service development.

3.	Project purpose, main aims

Project Proposal

- To move to the next stage of Modernising AHP careers to identify methods to:

- Identify potential  workforce solutions for optimising quality and productivity

- Identify opportunities for Staff progression

- Make a contribution to the DARZI  National next stage  review

- Use findings to give advice and direction the AHP arena through impact analysis and case study.

- Identify training needs

- Develop links with the Cancer Action Team

Skills for Health’s Strategic Intent will be achieved in a number of ways including working with partners to:

- Support the development of innovative, patient and user focussed service redesign and new ways of working, including the use of existing, extended and new roles within modernised healthcare careers

- Promote the use of competence based approaches to planning and development through the production of frameworks, products, tools and guides which have an excellent reputation for quality and ease of use.

- Demonstrate the benefits to the public, patients, service users and employers of a competence based approach to developing a more skilled, flexible and productive workforce.

- Identify possible innovative education, training & development solutions to reduce skills gaps.

- Champion the development of innovative education, training and development solutions, including e-learning.

Main Project Aims

- Demonstrate the strategic application of the national career framework.

Early implementation of the Modernising AHP careers using the tools launched as part of the AHP project to identify and test the following:

  - ‘Skill mix in MacMillan Cancer Rehabilitation and one other service. Apply the Calderdale Framework to the entire service with a focus on skill mix review and modernised service models’.

Apply the Calderdale Framework to an entire service based in Cancer services with a focus on modernised service models.

- Level 4- new role

Explore the development of a level 4 rehabilitation assistant practitioner in the Cancer rehab team and 1 other depending on local need.

Explore cancer and rehab therapist roles at career framework levels 5-7

4.	Scope of the project and key assumptions

The following table shows the initial assessment of the scope and deliverables from each project area

| Priority / Scope | Timescale / Deliverables / Outcomes | SHA/AHP lead / Actions |
| --- | --- | --- |
| 1. Skill mix Scope: The AHP’s required within the services | Timescale – 12months Deliverables : TBA Service Needs Analysis Functions/Competences identified Fitness for purpose – qualified & non qualified roles Productivity improvement identified New ways of working identified Workforce action plan Specify Learning programmes/qualifications Develop brief for use for commissioners Quality Assurance | TBA |
| 2.New level 4 role Scope: The AHP’s required within the services | Timescales 12 months Deliverables: TBA Service Needs Analysis Determine service inputs Functions/Competences identified New ways of working identified Fitness for purpose – qualified & non qualified roles Productivity improvement identified Workforce action plan Specify Learning programmes/qualifications Develop brief for use for commissioners | TBA |

5.	Project controls / management arrangements – including:

This project will be managed using a modified Prince 2 methodology. Skills for Health has standard programme and project management guidelines. These will be discussed with SHA/AHP sponsors and project controls agreed that are fit for purpose for this project. As a starting point the following functions will be put in place:

- A Strategy/Steering Group

- Project Board

- Quality Assurance process / reference groups (to be specified in relation to deliverables and projects

Appendix 3 comprises notes on the management controls that are used to establish SfH projects. The application of these for the joint project will need to be discussed and agreed.

An important aspect of the management controls will be to ensure that there are rules for making changes or escalation of issues

6.	Resources

£50,000 over period of 12 months

7.	Risks

The planning stage of this project will need to identify risks

8. Benefits realisation/impact assessment/equality impact assessment

These will be built into the project

9. Evaluation

This will be built into the project.

PROJECT OUTLINE

| PROJECT | Summary of work | Milestones | Timeframe |
| --- | --- | --- | --- |
| 1.Awareness raising | engage management, staff, commissioner, service user | December 08 | November 08- December 08 |
| 2.Service analysis | Identify functions and tasks to deliver service. Map to service user needs. Potential for new ways of working identified. Metrics identified | February 09 | January 09-February 09 |
| 3.Task analysis | use decision table to identify tasks suitable for delegation – level 3 and level 4, and tasks suitable for sharing cross profession. | February 09 | January 09-February 09 |
| 4.Competency Identification | Map to SfH, local, identify protocols needed. | April 09 | March 09 – June 09 |
| 4b. Competency generation | Rule & skill – NVQ3 Knowledge based - HEI Identify new ways of working. Map to AHP career framework | June 09 | March 09 – June 09 |
| 5. Supporting Systems | Local/regional : Local governance (Supervision/cpd) KSF/Job descriptions/ Unions National: HPC/CSP/COT/ McMillan | May 09 | January 09 – May 09 |
| 6.Training | competences (levels 3 and 4) Qualified staff (new ways of working) Validation via NVQ & HEI | July 09 | March 09 – July 09 |
| 7. Sustaining | Induction/PDR/KSF/standards. Write jobs as competency. based job descriptions/person spec with KSF levels/CPD to reflect above. Link with cancer action team. Evaluation. | Sept 09 | July – Sept 09 |
| Project Closure |  | October 09 | October 09 |

Skills for Health

Notes on Project Control Structures

Project Strategy Group - or alternative arrangements for ensuring that:

- The requirements of commissioners / sponsors are clear and are summarised in writing as a project mandate and / or specification

- Relevant specific policy considerations that are relevant to the project are taken into account

- The project is consistent with sponsor  and Skills for Health’s overall strategy and business plan

The Strategy Group should be advised if in the view of the project manager or project board, the project exceeds its mandate for any reason.

The project strategy group is the place where, for example:

- Home countries’ / local policy variations that affect the project are considered

- Differences in view about underlying models and principles between different strategic stakeholders

- Project boundaries and expectations are set

The broad aim of the Strategy Group is to ensure that the Project Board and Project Manager have a clear mandate and the project itself can accomplish its task without becoming embroiled in unnecessary supra-project issues and debate. The Strategy Group should address these outside of the project management arena.

Performance Management

The Skills for Health Programme Delivery Committee undertakes an overarching strategic role across the SfH work programme, reviewing mandates, receiving reports, signing off products and maintaining a strategic view across all aspects of Skill’s for Health’s work on behalf of the Main Board. Sponsors may wish to include other performance management mechanisms within the scope of the management controls

Project Board

The project executive group. A small group working with the project manager to ensure that any risks are identified and assessed and the project is delivered to time and within the financial target set. The project manager is accountable to the chair of the project board for successful delivery of the project. The core membership of the board will normally include:

- Chair or nominee of the Strategy Board

- Chair or nominee(s) of the Quality Assurance Group

- Project Manager

- Executive member as chair

The first task of the project board is to approve the project specification and plan. In many instances the specification and plan may be compiled before the project board meets. In any event, the board must satisfy itself about the achievability and robustness of the specification and plan and any work carried out up until the date of its first meeting as the basis for further work. If it is not satisfied that the plan can be delivered within the agreed resources and assumptions the project board must advise the Strategy Group.

Quality Assurance Group / Network

A group / network of direct and indirect product / service users, the main role of which is to ensure:

- That the content of the product is right

- That the product has good face validity amongst relevant stakeholder constituencies

- Fitness for purpose of the product.

- Implementability of the product

This group must be independent of the Project Board. Throughout their work members of QA groups and networks must ensure that they:

- Respect and protect the values, beliefs, security, privacy, confidentiality, and codes of practice of all stakeholders

- Declare any conflicts of interest arising from their work for the Skills for Health

- Do not actively market other services and / or products

The Quality Assurance Group will agree quality criteria for the products and determine how and when each product will be tested.  Where professionally recognised quality assurance frameworks are relevant to an area of work, these must be used.

APPENDIX2 –EXAMPLE COMPETENCY BASED JOB DESCRIPTION

Calderdale & Huddersfield NHS Foundation Trust

Clinical Therapy & Rehabilitation Directorate

JOB DESCRIPTION

## Post:

Assistant Practitioner (MacMillan Rehabilitation Team)

## Grade:

AfC Band 4

## Location:

Based at Calderdale Royal Hospital but working in the community across Calderdale & Huddersfield

## Responsible to:

MacMillan Cancer Rehabilitation Team Leader

## Job Purpose/Summary:

The post holder will be working with people who have been diagnosed with Cancer resulting in a temporary or permanent disability. Work includes treatment and care of patients and also their carer/relatives where relevant. The post holder will undertake highly skilled support work as part of the Macmillan Rehabilitation team, working under indirect supervision of the qualified Occupational Therapist and Physiotherapist. Work will be carried out in the users own home, residential care or other community venues. This will involve taking responsibility for an identified and delegated caseload following assessment by a therapist and will involve some independent decision-making. Intervention will include implementing treatment pathways, monitoring of patient progression and making significant alterations to patient treatment programmes as required. It may include leading and assisting with group exercise and advice sessions, supervising individual treatment programmes, assisting therapists with complex treatment, and carrying out particular treatment approaches, assessing ordering and issuing basic equipment. The post holder will be required to undertake lone working. Administrative duties and general patient care across departments are required.

Healthcare Associated Infection: Healthcare workers have an overriding duty of care to patients and are expected to comply fully with best practice standards. You have a responsibility to comply with Trust policies for personal and patient safety and for prevention of healthcare-associated infection (HCAI); this includes a requirement for rigorous and consistent compliance with Trust policies for hand hygiene, use of personal protective equipment and safe disposal of sharps. Knowledge, skills and behavior in the workplace should reflect this; at annual appraisal you will be asked about application of practice measures known to be effective in reducing HCAI.

## Main Duties and Responsibilities:

## Clinical

- Supports qualified staff in initial assessments.

- Plans & implements individual assessments & treatment pathways for patients requiring symptom management & exercise regimes, based on protocols.

- Organises, devises and amends/progresses treatment regimes.

- Manage a small non complex caseload, using reflection & analysis.

- Undertakes functional treatment programmes to progress the patients abilities in ADL.

- Able to assess, prescribe & fit equipment for patients with non complex functional problems.

- Observes patients response to treatment including any new problems & takes immediate action & seeks advice from qualified staff as appropriate.

- Educates carers and patients.

- Assists qualified staff in delivery of therapy programmes.

- Communicates effectively with colleagues, patients and carers, ensuring sensitivity is shown.

- Demonstrates listening skills

- Assist in toileting /personal care needs as required

- Maintain safe infection control by adhering to the Trust Infection Control Policy.

Educational

- Contribute to raising awareness of health & wellbeing with patients/carers.

- Seek & use appropriate support systems

- Contribute to own personal development

- Provide information & teaching

- Develop a good knowledge of the various cancer diagnoses & their treatments

- Participate in supervision

Organisational

- Able to take responsibility for the days work in the absence of qualified staff, seeking managerial & clinical advice & support appropriately.

- Assist in keeping departmental areas clean & tidy.

- Assist in maintaining a safe working environment for self, colleagues & patients.

- Organise & plan own workload, and assist in overall management of team workload.

- Contribute to audit.

- Participate in timely & accurate activity data & manage team data collection

- Responsible for specific administrative tasks

- Contribute to raising the profile of the service.

- Assist with orientation of new staff & students

## National Workforce Competences required

## Common to LEVEL 4 Roles:

GEN22: Communicate effectively with individuals

CfA106: Use IT to exchange information

HSC21: Communicate and complete records for individuals

HSC234: Ensure your own actions, support the equality, diversity, rights and responsibilities of individuals

HSC22: Support the health and safety of yourself and individuals

IPC2: Perform hand hygiene to prevent the spread of infection

HCS_D5: Comply with legal requirements for patient/client confidentiality

ENTO WRV1: Make sure your actions contribute to a positive and safe working culture

CHS118: Form a professional judgement of an individuals health condition

CHS 36: Provide basic life support

GEN4: Prepare individuals for healthcare activities

GEN6: Prepare the environment and resources for use during clinical/therapeutic activities

GEN7: Monitor and manage the environment and resources during and after clinical/therapeutic activities.

GEN8: Assist the practitioner to implement clinical/therapeutic activities.

GEN5: Support individuals undergoing healthcare activities

HSC241: Contribute to the effectiveness of teams

GEN23: Monitor your own work practices

CfA 105: Store and retrieve information

HSC23: Develop your knowledge and practice

GEN13: Synthesis new knowledge into the development of your own practice.

M&L D7: Provide learning opportunities for colleagues.

GEN36: Make use of supervision

AG2: Contribute to care planning and review

Specific to Rehabilitation Level 4 Role

GEN63: Act within the limits of your competence and authority

HSC24: Ensure your own actions, support the care, protection and well-being of individuals

HSC240: Contribute to the identification of the risk of danger to individuals and others

CHS168: Obtain a patient/client history

PSL5: Undertake an assessment or re-assessment of a patient

GEN75: Collaborate in the assessment of the need for, and the provision of, environmental and social support in the community

CHS142: Test individual’s abilities before planning exercise and physical activities.

CHS41: Determine a treatment plan for an individual.

CHS44: Plan activities, interventions and treatments to achieve specified health goals.

CHS135: Implement programmes and treatment for individuals who have restricted movement/mobility

CHS137: Implement mobility and movement programmes for individuals to restore optimum movement

CHS138: Assist in the implementation of mobility and movement programmes for individuals to restore optimum movement and function.

CHS 136: Assist in the implementation of programmes for individuals who have severely restricted movement/mobility

HSC223: Contribute to moving and handling individuals

GEN17: Contribute to the discharge of an individual into the care of another service

CHS11: Undertake personal hygiene for individuals unable to care for themselves

hfm_B3.1.7: Agree changes to interventions and treatments

GEN43: Monitor and review the rehabilitation process with the individual, their family, carers and other professionals

CHS55: Facilitate the individuals management of their condition and treatment plan

GEN 36: Make use of supervision

GEN12: Reflect on and evaluate your own values, priorities, interests and effectiveness

GEN14: Provide advice & information to individuals on how to manage their own condition

LLUK L11: Enable learning through demonstrations and instruction

HSC329: Contribute to planning, monitoring and reviewing the delivery of service for individuals CHS138: Assist in the implementation of mobility and movement programmes for individuals to restore optimum movement and functional independence

HSC3100: Participate in inter-disciplinary team working to support individuals

HSC352: Support individuals to continue therapies

GEN8: Assist the practitioner to implement healthcare activities

HSC226: Support individuals who are distressed

HSC350: Recognise, respect and support the spiritual wellbeing of individuals

APPENDIX 3: EXAMPLE OF LEVELLING TO AHP CAREER FRAMEWORK

MacMillan Worker Band 4 - 16/12/2009

| CF Scores |  |
| --- | --- |
| Descriptor scores | D Level |
| 1. Knowledge, Skills, Training & Experience | 4 |
| 2. Supervision | 4 |
| 3. Professional and vocational competence | 3 |
| 4. Analytical / Clinical Skills and Patient Care | 4 |
| 5. Organisational Skills and Autonomy/Freedom to Act | 4 |
| 6. Planning, Policy and Service Development | 4 |
| 7. Financial, Administration, Physical and Human Resources | 4 |
| 8. Research and Development | 2 |
| Overall | 4 |
| Expected CF level (where an opinion made) |  |

| S1 | JobID |  |  |
| --- | --- | --- | --- |
| MacMillan Worker Band 4 | Job Title |  |  |
| Rehab | Key Function |  |  |
| Cancer | Health Area(s) |  |  |
| Rehab team | Staff Grouping |  |  |
| Calderdale & Huddersfield | Trust |  |  |
| 16/12/2009 | Date |  |  |
| 1. Knowledge, Skills, Training & Experience | Level |  |  |
| Recalls basic general knowledge and uses language, literacy, numeracy and information technology to carry out straight forward tasks. AND Shows understanding of a small number of routine work procedures gained through short induction or on the job training. | 1 |  | Devises and amends progresses treatment regimes using own imitative and established knowledge and skills. Instruct patients and carers assess and prescribe equipment for non complex problems, demonstrate listening skills, provides information and teaching Develops thro formal and informal knowledge and training knowledge of cancer, manage data collection system Able to take responsibility for the days work in the absence of qualified staff seeking managerial advice and support appropriately |
| Uses skills and key competences to carry out tasks where action is governed by rules defining routines and processes and recalls and comprehends basic knowledge of a work area. - The range of knowledge involved is limited to facts and main ideas OR Selects and applies basic methods, tools and strategies. And Recalls and comprehends basic knowledge of a work area. - The range of knowledge involved is limited to facts and main ideas | 2 |  |  |
| Applies knowledge to a work area that includes processes, techniques, materials, instruments, equipment, terminology and some theoretical ideas AND evaluates different approaches to tasks OR Uses a range of work area-specific skills to carry out tasks and show personal interpretation through selection and adjustment of methods, tools and materials AND evaluates different approaches to tasks. | 3 |  |  |
| Uses a wide range of work area-specific practical and theoretical knowledge. AND Evaluates outcomes in terms of planned approach used. OR Develops planned approaches to tasks that arise in work or study by applying specialist knowledge and using expert sources of information AND evaluates outcomes in terms of planned approach used. | 4 | x |  |
| Uses broad theoretical and practical knowledge that is often specialised within a field and shows awareness of limits to knowledge base AND demonstrates ability to transfer theoretical and practical knowledge in creating solutions to problems OR Uses broad theoretical and practical knowledge that is often specialised within a field and shows awareness of limits to knowledge base. Develops planned and creative responses in researching solutions to well defined concrete and abstract problems. | 5 |  |  |
| Uses detailed theoretical and practical knowledge of a work area AND utilises some knowledge that is at the forefront of the work area and will involve a critical understanding of theories and principles AND Devises and sustains arguments to solve problems OR Uses detailed theoretical and practical knowledge of a work area AND demonstrates mastery of methods and tools in a complex and specialised work area and demonstrate innovation in terms of methods used AND devises and sustains arguments to solve problems. | 6 |  |  |
| Utilises highly developed specialised knowledge covering a range of procedures and underpinned by relevant broad based knowledge, experience and competence AND develops new skills in response to emerging knowledge and techniques OR Uses highly specialised theoretical and practical knowledge some of which is at the forefront of knowledge in the work area. This knowledge forms the basis for originality in developing and/or applying ideas AND develops new skills in response to emerging knowledge and techniques OR Demonstrates critical awareness of knowledge issues in the work area and at the interface between different or new work areas, creating a research based diagnosis to problems by integrating knowledge. AND Making judgements with incomplete or limited information developing new skills in response to emerging knowledge and techniques. | 7 |  |  |
| Uses highly developed specialised knowledge to critically analyse, evaluate and synthesise new and complex ideas that are at the most advanced frontier of a work area AND extends or redefines existing knowledge and/or professional practice within a work area or at the interface between work areas OR uses highly developed specialist/specialised knowledge to critically analyse, evaluate and synthesise new and complex ideas that are at the most advanced frontier of a work area AND researches, conceives, designs, implements and adapts projects that lead to new knowledge and new procedural solutions PLUS Applies advanced specialist knowledge across a work area or over more than one work areas acquired over a long period OR in-depth & advanced specialist knowledge, experience and competence | 8 |  |  |
| Applies advanced and highly developed theoretical and practical knowledge over a wide range of clinical, scientific, technical and/or management functions OR Is accountable for ensuring all staff within area of responsibility have required skills and knowledge to deliver products of the highest standard and facilitate effective knowledge management to ensure evidence based practice and quality assurance. | 9 |  |  |

| 2. Supervision | Level |  |  |
| --- | --- | --- | --- |
| Works under direct supervision and demonstrates personal effectiveness in straight forward and stable contexts. | 1 |  | Able to take responsibility for the days work in the absence, seeks advice and support appropriately |
| Works under close but not continuous supervision AND takes limited responsibility for improvements in performance in work contexts and within familiar, homogeneous groups. | 2 |  |  |
| Takes responsibility for completion of tasks and demonstrates some independence in work where contexts are generally stable but where some factors change. - which could include limited supervisory responsibilities. | 3 |  |  |
| Manages role under guidance in work contexts that are usually predictable and where there are many factors involved that cause change and where some factors are interrelated AND makes suggestions for improvement to outcomes. OR Ongoing supervision of routine work of others AND makes suggestions for improvement to outcomes. | 4 | x |  |
| Manages work independently that require problem solving where there are many factors some of which interact and lead to unpredictable change. OR Shows creativity in developing work, work is managed rather than supervised; OR appraise performance of others | 5 |  |  |
| Manages team and resources in environments that are unpredictable and require that complex problems are solved where there are many interacting factors OR Demonstrates leadership for a work area. OR Shows creativity in developing projects and shows initiative in management processes that includes the development of others to develop team performance. | 6 |  |  |
| Demonstrates leadership and innovation in work contexts that are unfamiliar, complex and unpredictable and that require solving problems involving many interacting factors. OR Reviews strategic impact/outcome of the work or team. | 7 |  |  |
| Demonstrates substantial leadership, innovation and independence in work contexts that are novel and require the solving of problems that involve many interacting factors. | 8 |  |  |
| Take overall responsibility for service area, ensuring goals, targets including financial and quality benchmarks are achieved. AND Interprets national policy and strategy to set goals and standards and directs services with responsibility and accountability OR Interprets national policy and strategy to set goals and standards and directs services with responsibility and accountability AND provides leadership across a number of areas bringing strategic direction, innovation and influence through work practice. | 9 |  |  |

| 3. Professional and vocational competence | Level |  |  |
| --- | --- | --- | --- |
| Accepts guidance on work practice. AND demonstrates awareness of procedures for solving problems. | 1 |  | Contributes to own personal development. Assess and prescribe equipment for patients with non complex functional problems. Demonstrates listening skills and deals sensitively with individuals concerns |
| Seeks guidance on work practice AND solves problems using information provided. | 2 |  |  |
| Takes responsibility for own development and work practice AND solves problems by integrating information from expert sources taking account of relevant social and ethical issues. | 3 | x |  |
| Demonstrates self-directed development and work practice AND Solves problems by integrating information from expert sources taking account of relevant social and ethical issues. | 4 |  |  |
| Evaluates own practice and identifies development. Formulates responses to abstract and concrete problems. OR Evaluates own practice and identifies development. Demonstrates experience of operational interaction within a work area. OR Evaluates own practice and identifies development. Makes judgements based on knowledge of relevant social and ethical issues. | 5 |  |  |
| Consistently evaluates own practice and identifies development needs. AND Gathers and interprets relevant data in a work area to solve problems. Makes judgements based on social/ethical issues that arise in work or study. OR Consistently evaluates own practice and identifies development needs AND Demonstrates experience of working within a complex environment AND Makes judgements based on social/ethical issues that arise in work or study. | 6 |  |  |
| Demonstrates independence in the direction of practice and a high level understanding of development processes. AND Responds to social/scientific, clinical/ethical issues that are encountered in work or study AND manages change within a complex environment Demonstrates independence in the direction of practice responding to social scientific clinical and ethical issues that are encountered in work or study AND High level understanding of development processes OR Demonstrates independence in the direction of practice responding to social scientific clinical and ethical issues that are encountered in work or study AND Solves problems by integrating complex knowledge sources that are sometimes incomplete and in new and unfamiliar contexts OR Demonstrates independence in the direction of practice responding to social scientific clinical and ethical issues that are encountered in work or study AND Manages change within a complex environment | 7 |  |  |
| Demonstrates sustained commitment to development of new ideas or processes and a high level understanding of development processes. AND Promotes social/ethical advancement through actions. OR Critically analyses, evaluates and synthesises new and complex ideas and makes strategic decisions based on these processes. AND Promotes social/ethical advancement through actions. OR Carries out operational interactions with strategic decision making capacity within a complex environment. AND Promotes social/ethical advancement through actions. | 8 |  |  |
| Takes overall responsibility for service area, department or clinical pathway - to include financial and managerial responsibility. AND Critically analyses, evaluates and synthesises new and complex ideas and makes strategic decisions based on these processes. AND Demonstrates experience of operational interactions with strategic decision making capacity within a complex environment AND Carries responsibility for policy implementation formulating long term strategic plans impacting across or beyond the organisation | 9 |  |  |

| 4. Analytical / Clinical Skills and Patient Care | Level |  |  |
| --- | --- | --- | --- |
| Performs limited tasks in a narrow area. | 1 |  | Undertakes physical and functional treatment, assess and prescribe equipment for patients with non complex |
| Performs clinical, technical, administrative, or scientific tasks in a narrow area. OR Makes judgments involving straight-forward work-related facts or situations. | 2 |  |  |
| Performs a wider range of protocol driven clinical, technical, administrative or scientific tasks OR Makes judgements some of which require comparison of options | 3 |  |  |
| Performs clinical, technical, administrative or scientific procedures AND Makes judgements requiring a comparison of options. | 4 | x |  |
| Makes judgements requiring analysis, interpretation and comparison of options OR Performs broad range of clinical, technical or scientific procedures. | 5 |  |  |
| Provides specialist clinical, technical or scientific services and/or advice. OR Makes judgements involving a range of complex facts, options, analysis and interpretation | 6 |  |  |
| Provides highly specialist clinical, technical and/or scientific services Makes complex judgements. OR Provides specialist clinical, technical and/or scientific services across a work area. Makes complex judgements. OR accountable for direct delivery of part of service. Makes complex judgements. | 7 |  |  |
| Provides highly specialist clinical, technical or scientific services and/or advice, across a work area. AND IS Able to act as an expert in one or more service areas OR Makes complex or highly complex judgements AND is able to act as an expert in one or more service areas. | 8 |  |  |
| Provides clinical, technical, and scientific expertise and leadership which may be recognised at national and/or international level. OR Has corporate responsibility or lead provision of clinical, technical or scientific services which may extend beyond employing organisation. | 9 |  |  |

| 5. Organisational Skills and Autonomy/Freedom to Act | Level |  |  |
| --- | --- | --- | --- |
| Works to established procedures / protocols under direct supervision. | 1 |  | Takes responsibility for daily running of specific aspect of a service, seeks managerial advice and support appropriately, organises and plans own workload |
| Works to established procedures / protocols, work is supervised. OR organizes own day to day work activities and tasks, work is supervised | 2 |  |  |
| Work within established procedures / protocols. Supervision is readily available OR. Organise work tasks of others. | 3 |  |  |
| Plans straightforward tasks AND Work guided by standard operating procedures / protocols. | 4 | x |  |
| Plan, organise and prioritise own work, activities and more complex tasks. | 5 |  |  |
| Works independently and directs work activities of a team or others. | 6 |  |  |
| Responsible for work area, specialist services or clinical pathways. OR accountable for direct delivery of part of service. | 7 |  |  |
| Direct and influence commissioning and/or service provision. OR be accountable for direct delivery of a service/s. | 8 |  |  |
| Has responsibility and accountability for services, setting goals, standards and direction by interpretation of strategic policy and national strategy. | 9 |  |  |

| 6. Planning, Policy and Service Development | Level |  |  |
| --- | --- | --- | --- |
| Follows procedures determined by others. Can’t separate 1&2 | 1 |  | Contributes to developing a specific area of service in liaison with qualified staff |
| Follows procedures determined by others. | 2 |  |  |
| Offers comments/suggestions for improvements to procedures or possible service developments. | 3 |  |  |
| Formally comments/makes suggestions on procedures or possible service developments OR proposes changes to working practices or procedures for own work area. | 4 | x |  |
| Develop procedures and changes working practices or procedures for own work area. | 5 |  |  |
| Implement policy and propose/ changes working practices or procedures. OR plans complex activities involving liaison with others and/or over long time periods. | 6 |  |  |
| Proposes changes to practices or procedures which impact beyond own work area OR May plan and/or organise a broad range of complex activities or programmes with formulation of strategies. | 7 |  |  |
| Develop and implement policy and service developments which impact beyond own area of responsibility beyond organisation. | 8 |  |  |
| Responsible for policy implementation and policy or service development at directorate/division or organisational level or with other organisations and agencies. This involves formulating long term strategic plans impacting across or beyond organisation. | 9 |  |  |

| 7. Financial, Administration, Physical and Human Resources | Level |  |  |
| --- | --- | --- | --- |
| Observes personal duty of care in relation to equipment and resources used in course of work. | 1 |  | monitors and maintains stock, provides information and teaching internally and externally |
| Responsible for care of equipment used by self or others. | 2 |  |  |
| Assist in or carry out training related to own work activity. OR Responsible for maintaining stock. OR have financial responsibility within strict guidelines | 3 |  |  |
| Responsible for safe use of highly complex equipment. OR Takes some responsibility for the training of others and may deliver training. OR Undertakes financial transactions working within organisational processes and policies. | 4 | x |  |
| Works within organisational processes and policies for financial and human resource activities OR Trains others and develops team performance. OR Manages people and reviews performance of self and others. OR Contributes to administration and management of work area or department. | 5 |  |  |
| Holds a delegated budget OR be responsible for purchasing / maintenance of assets OR Undertakes supervision and is responsible for teaching and training inside/outside work area. | 6 |  |  |
| Devise training or development programmes. OR responsible for work area budget OR Manages staff and/or services ranging in size and complexity. | 7 |  |  |
| Responsible for overall delivery of teaching and training programmes. OR a budget holder for one or more services and responsible for physical assets. | 8 |  |  |
| Responsibility for delivery against local and national quality, financial and performance frameworks. | 9 |  |  |

| 8. Research and Development | Level |  |  |
| --- | --- | --- | --- |
| Contributes to simple audits or surveys relevant to own work area. | 1 |  | contributes to relevant audit projects |
| Performs simple audits or surveys relevant to own work area. | 2 | x |  |
| Performs simple audits or surveys and assist with occasional clinical trials or research projects. | 3 |  |  |
| Assist with clinical trials or research projects within own work area OR Evaluate equipment, techniques and procedures | 4 |  |  |
| Undertake straightforward or complex audit or assist with clinical trials or research projects. | 5 |  |  |
| Carry out R&D as a major activity AND regularly undertake clinical trials or research projects. | 6 |  |  |
| Initiate and develop R&D programmes. | 7 |  |  |
| Implement R&D programmes OR Initiate and develop programmes with external impact. | 8 |  |  |
| Takes overall responsibility for coordination of R&D programmes. | 9 |  |  |

APPENDIX4- EXAMPLE NTR

Better Skills

Better Jobs

Better Health

Nationally Transferable Roles Template

Assistant Practitioner

Definition of the Assistant Practitioner

An assistant practitioner is a worker who competently delivers health and/or social care to and for people.  They have a required level of knowledge and skill beyond that of the traditional healthcare assistant or support worker.  The assistant practitioner would be able to deliver elements of health and social care and undertake clinical work in domains that have previously only been within the remit of registered professionals.  The assistant practitioner may transcend professional boundaries.  They are accountable to themselves, their employer, and more importantly, the people they serve.

The job description of the assistant practitioner should equate to Level 4 on the career framework.

Definition

And

The characteristics of an assistant practitioner have been developed by Skills for Health working with focus groups of employers and other stakeholders.

Further information regarding assistant practitioner roles has been used to support the findings of recent focus groups.

References:

2006 Ferrier C. and Snewin S., Associate practitioner biomedical scientist - An employer’s toolkit The Biomedical Scientist pp253-254 March 2006

2007 Federation for Healthcare Science, Statement on the role of associate practitioner http://www.FHCS_statement_on_associate_practitioners_nov07

2007 The Society of Radiographers, The scope of practice of assistant practitioners in clinical imaging, First edition January 2007

2008 NHS Education for Scotland, A Guide to Health Care Support Worker Education and Role Development Consultation Document

Huddleston M. & Scions H (2006) Assistant Theatre Practitioners: ‘must have’ or ‘needs must’. The Journal of Perioperative Practice Vol 16, no 10, p 482

NHS Northwest (2007) Assistant Practitioner Degree Evaluation Project

NHS South Central (2008) Evaluation of Assistant/Associate Practitioner Roles across NHS South Central

This section of the template has an example of an assistant practitioner role.  This example is intended to give core information for the role and to enable localities to add to the specific competences as dictated by the role undertaken.  The indicative learning and development packages are included.

All assistant practitioner roles will have the following common/core competences.  Specific competences to the role have then been identified for each role.   Any additional competences specific to the locality should then be identified locally and added to the template using the same format.

Common/Core Competences:

| Underpinning Principle | Reference Function | Competence |
| --- | --- | --- |
| 1. Communication | 1.2, Communicate effectively | GEN 22 Communicate effectively with Individuals CfA 106 Use IT to exchange information HSC 21 Communicate and complete records for individuals |
| 2. Equality & Diversity | 2.5,Ensure your own actions support the equality diversity rights and responsibilities of individuals | HSC 234 Ensure your actions support equality, diversity and responsibilities of others |
| 3. Health, Safety & Security | 3.9 Support the health and safety of yourself and individuals 3.8 Ensure your own actions reduce the health and safety risk to others Miscellaneous | HSC 22 Support health and safety of self and others IPC2 Perform hand hygiene to prevent the spread of infection HSC D5 Comply with legal requirements for confidentiality |
| 4. Safeguard and Protect Individuals | 4.2 Make sure your actions support the care, protection and well being of others | ENTO WRV1 Make sure your actions contribute to a positive and safe working culture |
| A Assessment and Investigation of Health | A.2.10.1 Determine a diagnosis and prognosis for an individual | CHS 118 Form a professional judgement of an individual’s health |
| B Planning for and addressing health requirements. | B2.2.1 Provide life support B.1.1.3 Prepare individualised treatment plans for individuals B2.1.3 Prepare individuals for healthcare actions B2.1.5 Prepare environments for use during healthcare delivery B2.1.7 Monitor and manage the environment and resources during and after healthcare activities B2.1.8 Support others in providing healthcare actions B2.9.1 Support individuals during and after clinical/therapeutic activities | CHS 36 Provide basic life support AG2 Contribute to care planning and review GEN 4 Prepare individuals for clinical/therapeutic activities GEN 6 Prepare the environment and resources for use during clinical/therapeutic activities GEN 7 Monitor and manage the environment and resources during and after clinical/therapeutic activities GEN 8 Assist the practitioner to implement clinical/therapeutic activities GEN5 Support individuals during and after clinical/therapeutic activities |
| G: Management of the provision of health care. | G1.3.1 Contribute to the effectiveness of teams G1.3.7 Allocate and check work within your team G1.7 Audit your own clinical practice G2.1.3 Maintain file stores | CfA 106 Use IT to exchange information HCS 241 Contribute to the effectiveness of teams H&L D5 Allocate and check work within your Team GEN 23 Audit your own work practice CfA 105 Store and Retrieve Information |
| H. Education and learning around health. | H2.1 Develop your knowledge and practice H2.3. Synthesis new knowledge into the development of your own practice H.3.5 Provide learning opportunities for colleagues | HSC 23 Develop your knowledge and practice GEN13 Synthesis new knowledge into the development of your own practice M&L D7 Provide learning opportunities for colleagues |

Basic Information

| Named Role | Assistant Practitioner – Orthopaedic Rehabilitation Assistant (Early Discharge Team) |
| --- | --- |
| Clinical Pathway | Orthopaedic |
| Sample Job Description Available | Yes |
| Experience required | Minimum 2 years experiences as Rehab Assistant Band 3 or 3 years in relevant field Experience of working in the community |
| Career Framework Level | 4 |

Specific Competences:

| Underpinning Principle | Reference Function | Competence |
| --- | --- | --- |
| Safeguard and protect individuals (underpinning principle) | 4 - Safeguard and protect individuals (underpinning principle) | GEN63: Act within the limits of your competence and authority HSC24: Ensure your own actions, support the care, protection and well-being of individuals HSC240: Contribute to the identification of the risk of danger to individuals and others |
| Assessment and Investigation of health | A - Assessment and Investigation of health | PSL5: Undertake an assessment or re-assessment of a patient GEN75: Collaborate in the assessment of the need for, and the provision of, environmental and social support in the community CHS168 Obtain a patient/client history CHS142: Test individuals abilities before planning exercise and physical activities |
| Planning/preparation for and addressing of health requirements | B - Planning/preparation for and addressing of health requirements | CHS41: Determine a treatment plan for an individual CHS44: Plan activities, interventions and treatments to achieve specified health goals CHS137: Implement mobility and movement programmes for individuals to restore optimum movement HSC223: Contribute to moving and handling individuals CHS11: Undertake personal hygiene for individuals unable to care for themselves GEN17: Contribute to the discharge of an individual into the care of another service hfm_B3.1.7: Agree changes to interventions and treatments GEN43: Monitor and review the rehabilitation process with the individual, their family, carers and other professionals CHS55: Facilitate the individuals management of their condition and treatment plan |
| Education and learning around health | H - Education and learning around health | GEN36: Make use of supervision GEN12: Reflect on and evaluate your own values, priorities, interests and effectiveness GEN13: Synthesise new knowledge into the development of your own practice GEN14: Provide advice & information to individuals on how to manage their own condition LLUK L11: Enable learning through demonstrations and instruction |
| Management and administration of health care | G - Management and administration of health care | HSC3100: Participate in inter-disciplinary team working to support individuals |

Locality Specific Competences

In this space you can define additional competences which are essential for your local needs.

Go to the Health Functional Map to begin your search for the competences related to the additional tasks or functions you have identified.

All competences are cross referenced to the knowledge and skills framework (KSF)

| Underpinning Principle | Reference Function | Competence |
| --- | --- | --- |
| Planning /preparation for & addressing of health requirements | B – Planning /preparation for & addressing health requirements | HSC226: Support individuals who are distressed |
|  |  | HSC352: Support individuals to continue therapies |

Indicative Learning and Development

Nationally transferable roles may be underpinned by a range of learning and development activities to ensure both competence and role confidence.  The learning and development included within the template is by nature indicative.  In some cases it is endorsed by professional bodies and/or special interest groups and accredited by an awarding body.

| Nationally transferable role | Assistant Practitioner - Orthopaedic Rehabilitation Assistant (Early Discharge Team) |
| --- | --- |
| Formal endorsed learning | Certificate of Higher Education – Reablement (or equivalent) |
| Informal learning | A range of informal learning opportunities will be appropriate including reflective practice, shadowing, attendance only courses |
| Summary of learning and development including aims and objectives | Shell award: work based learning accredited up to 60 credits. 3 further 20 credit modules. |
| Duration | Varies depending on learners previous experience & knowledge |
| National Occupational Standards/National Workforce Competences used | Local work based competencies (derived from Calderdale Framework) underpin national occupational Standards |
| Credits (including framework used) | 120 credits at certificate level (shell award) |
| Accreditation |  |
| APEL and progression | Completion of certificate of Higher Education should enable progression to Foundation/undergraduate degree. Shell award facilitates incremental progression and accreditation of work based learning |
| Programme structure | Blended learning including significant work based learning and assessment component, e-learning and delivered materials (HEI) |
| Resources required, e.g. placement learning, preceptors, accredited assessors etc | Formal, protected study time. Work based teaching & assessment, supervision & mentoring HEI mentoring |
| Quality Assurance | Through HEI or FE college |
| Policies included in programme documentation | Equal opportunities, equality & diversity and accessibility Appeals procedure |
| Funding | To be agreed locally |
| Leading to registration or membership with: | Currently N/A |

Characteristics of the Assistant Practitioner will include some or all of these:

Knowledge / skills

Use of a wide range of work area-specific practical and theoretical knowledge, which informs the approach planned to tasks that arise in work and /or study.

- Evaluates outcomes in terms of the –planned approach used.

- Demonstrates self-directed development and work practice

Leadership / management

Manage their role under guidance in work contexts that are usually predictable and where there are many factors involved that cause change and where some factors are interrelated.

- Work is guided by standard operating procedures / protocols

- Plans straightforward tasks

Innovation / decision making

- Formally comments/makes suggestions on procedures or possible service developments

- Proposes changes to working practices or procedures for own work area.

- Solves problems by integrating information from expert sources taking account of relevant social and ethical issues.

In order to:

- Perform clinical, technical, administrative or scientific procedures

- Make judgements requiring a comparison of options

- Make suggestions for improvement to outcomes.

Assistant Practitioners may:

- May supervise routine work of others

- Be responsible for safe use of highly complex equipment.

- Takes some responsibility for the training of others and may deliver training.

- Undertake financial transactions working within organisational processes and policies.

- Evaluate equipment, techniques and procedures

- Assist with clinical trials or research projects within own work area.

Source: Skills for Health CF team.

Further Information

If you would like further information on this role please contact the Skills for Health’s Policy Implementation Team on 0121 767 1388 or alternative you can speak to the Calderdale Framework Team at the Calderdale and Huddersfield NHS Foundation Trust on 01422 305570

APPENDIX 5- INDEX OF LOCAL COMPETENCIES

MACMILLAN COMMUNITY TEAM LEVEL 3 COMPETENCY

INDEX

When to Stop

Mobility & Walking Aids
     - Normal walking without aids

-  1 Stick
- 2 Sticks

-  Crutches
- Walking Frame
- Wheeled Walking Frame

Stairs Practice
  - None Weight Bearing
-    Partial Weight Bearing
-    Full Weight bearing

Equipment:

- General Background Information

- Bathing Equipment

- Fitting & Practising with a bed leaver

- Toilet Equipment
- On/ Off Toilet
- Fitting a Raised Toilet Seat
- Fitting a Stirling Toilet Frame
- Free Standing Toilet Frame

- Commode

- Perch Stool

- Trolley

- Catheter Care
- Attaching an overnight bag to leg bag
- Changing an overnight bag to leg bag
- Emptying a catheter bag
- Removing an overnight from a leg bag

Washing & Dressing

- Washing Practice

- Getting dressed when one arm is weaker

- Stocking Aid

- Using a Brevetti Aid

- Helping Hand

- Long Handled Shoe Horn

Kitchen Tasks

Functional Exercises:

- Reaching in Sitting & Standing

- Turning in Bed

- Lying to Sitting

- Standing with Theraband

- Calf Raisers

- Sit to stand (inc. neurological movement pattern)

- Side Stepping/Sideways Walk

- Marching on the Spot

- Forward Step Ups

- Sideways Step Ups

- Standing Unsupported

- Single Leg Stand

- Stepping

- Toe Touch

- Lunging

- Backward Chaining

- Core Stability Exercises

- Attention Training

Stretches

- Calf Gastrocnemius Stretches

- Occiput Stretch

- Positioning Stroke patients

- How to care for upper Limb in stroke patients Bed & Chair

Lower Limb Exercises

- Calf

- Resisted leg Exercises

- Clam

- Toe Raise

- Hip Abduction in sitting

- Hip abduction in lying

- Hip abs in standing

- Hamstring Curls

- Knee Flexion (Lying and Sitting)

- Hyper extension of Knee

- Hip Abduction/ Flexion / Extension

- Ankle Dorsi/Planter Flexion

- Static gluteals

- Static quads

- Inner range Quads

- Straight leg raise

Upper Limb Exercises

- Shoulder

- Elbow

- Hand Activity

Outdoor Mobility

- Outdoor Mobility

- Preparation for Home Visits

- Negotiating Threshold

- Shopping On Foot

- Public Transport

- Key Safe

Ice / Heat Treatment

  - Cryocuff

Miscellaneous Information:

    - Goniometer

    - CPM

    - Hip Precautions

LEVEL 4 ASSESSMENT COMPETENCY INDEX

(INCLUDING SUPPORTING COMPETENCIES)

- MOBILITY & WALKING AID ASSESSMENTS

  - Stick(s)

  - Elbow Crutches

  - Frame

  - Rollator

- STAIR CLIMBING ASSESSMENT

  - Advice

  - Bath Step

  - Rails

  - Banisters

  - Stairlift check of

- OUTDOORS ACCESS ASSESSMENT

  - Grab rails

  - Outside rails

  - (Shallow step)

4.  OUTDOOR MOBILITY ASSESSMENT

- 4 Wheeled Walker

5.  BATHING TRANSFER ASSESSMENT

  - Bathboard +/- seat

  - Rails

  - Swivel Bather

  - Over bath shower

  - Powered bathing solutions

- BED TRANSFER ASSESSMENT

  - Bed Leaver/Loop

  - Rails

  - Bed raisers

  - Step

  - Leg Lifter (manual)

  - Over bed pole

  - Rope Ladder

  - Mattress Elevator (MacMillan)

- HOT DRINK & MEAL PREPARATION ASSESSMENT

- Advice

- Small Equipment

- Perch Stool

- Trolley

- SEATING TRANSFER ASSESSMENT

  - Chair/Settee raisers

  - Plinth

- SHOWER TRANSFER ASSESSMENT

- Rails

- Drop down shower seat

- Shower chair

- TOILET TRANSFER ASSESSMENT

- Raised toilet seat

- Rails

- Toilet frame (free standing/fixed/Sterling)

- Commodes (including mobile).

- PAIN ASSESSMENT

- RANGE OF MOVEMENT AND STRENGTH ASSESSMENTS

- EXERCISE

- MACMILLAN SPECIFIC

- Fatigue

- Anxiety

- Breathlessness

- RAH SPECIFIC

- Wound care

LEVEL 6/7 BLURRED BOUNDARY ASSESSMENT COMPETENCY INDEX

(INCLUDING SUPPORTING COMPETENCIES)

- MOBILITY & WALKING AID ASSESSMENTS

  - Stick(s)

  - Elbow Crutches

  - Frame

  - Rollator

- STAIR CLIMBING ASSESSMENT

  - Advice

  - Rails

  - Banisters

- OUTDOORS ACCESS ASSESSMENT

  - Grab rails

  - Outside rails

  - (Shallow step)

4.  OUTDOOR MOBILITY ASSESSMENT

- 4 Wheeled Walker

5.  BATHING TRANSFER ASSESSMENT

  - Bathboard +/- seat

  - Rails

  - Swivel Bather

  - Over bath shower

  - Powered bathing solutions

- BED TRANSFER ASSESSMENT

  - Bed Leaver/Loop

  - Rails

  - Bed raisers

  - Step

  - Leg Lifter (manual)

  - Over bed pole

  - Mattress Elevator (MacMillan)

  - Profile Bed

- HOT DRINK & MEAL PREPARATION ASSESSMENT

- Advice

- Small Equipment

- Perch Stool

- Trolley

- SEATING TRANSFER ASSESSMENT

  - Chair/Settee raisers

  - Plinth

- SHOWER TRANSFER ASSESSMENT

- Rails

- Drop down shower seat

- Shower chair

- TOILET TRANSFER ASSESSMENT

- Raised toilet seat

- Rails

- Toilet frame (free standing/fixed/Sterling)

- Commodes (including mobile).

- PAIN ASSESSMENT

- STRENGTH ASSESSMENTS

- GONIOMETRY

- ASSESSMENT OF HIP ROM

- ASSESSMENT OF TREM??? RG SIGN

- ASSESSMENT FOR LEG LENGTH DESCREPANCY

- ASSESSMENT FOR HIP FLEX CONTRACTURE

- ASSESSMENT OF KNEE ROM

- ASSESSMENT OF POST OPERATIVE SWELLING

- APPLICATION OF CRYOCUFF

- WOUND CARE

- ASSESSMENT OF FATIGUE

- ASSESSMENT OF ANXIETY

- ASSESSMENT OF BREATHLESSNESS

- PACING AND ENERGY CONSERVATION

- FAB DIARY

- SLEEP HYGIENE

- FIRST LINE ADVISE NUTRITION AND HYDRATION

- PATIENT CENTRED GOAL SETTING

- RELAXATION TECHNIQUES

- RE-EDUCATION

- REHABILITATION ACTIVITIES

- INIALERS, NEBULISERS & O2

- POSITIONING

- ACBT

- BREATHING CONTROL

- EXERCISE PRESCRIPTION / PROGRESSION

- INTERPERSONAL SKILLS – ADVANCED COMMUNICATION SKILLS

- (END OF LIFE)

- FIRST LINE DIETETIC ADVICE

- COGNITIVE – CAMS.

APPENDIX 6:CERTIFICATE IN REABLEMENT

CASE STUDY; MICHELLE

Michelle is a 49 year old mum of 3 working in rehabilitation support.

- No formal qualifications on employment

- 3 years experience as a Band 2 Therapy Assistant (hospital based)

- Undertook core work based competency training

- Undertook service specific work based competency training

- Secured promotion to Band 3 Therapy Assistant (community based)

- Fast track NVQ 3 (be APEL of competencies)

- On completion secured promotion to Band 4 Therapy Assistant Practitioner (community based)

- Currently undertaking assistant practitioner work base competency training

- Awaiting enrolment to certificate in reablement at Bradford University

- On completion of certificate in reablelemn Michelle will have the knowledge to support her work based skills and therefore fulfil her role as an assistant practitioner.

‘The Assistant Practitioner delivers elements of health and social care in domains that have previously only been the remit of registered professionals’.

Meeting 10.00am Friday 13th November 2009

Laura Mitchell Health Centre

Review and evaluation of the evidence for accreditation of prior experiential learning implicit in the Calderdale Framework (level 4 competencies)

Attendance:

Jayne Duffy		Project Lead Calderdale framework

Rachael Smith 	Project Lead Calderdale framework

Jane Kettle		ESCALATE & Higher Education Academy

Jane Priestly		School of Health Studies, University of Bradford

Vicki Illingworth	ESCALATE, University of Bradford

Attendance 1.30 – 2.30pm for information on quality assurance:

Bev France	Head of Training and Development, Calderdale & Huddersfield HNS Foundation Trust

Kathy Westgate	Assistant Head of Training and Development, Calderdale & Huddersfield NHS Foundation Trust

Aim of the meeting: to review, evaluate and assess the evidence provided by the competency based training of the Calderdale framing and the associated experiential learning, in relation to achieving credit recognition for units of learning on the proposed Certificate in Reablement Support.

Health Safety and Security:  20 credits

Evidence

- Induction to trust 0.5day

- Induction to the Directorate.  Delivered over 6 weeks in the workplace

- Manual handling training 3 days with 1 day annual update.  Scenario based delivery to identity risk, use clinical reasoning and application of theory to practice.

- Risk management 1 day

- CPR observed and tested 0.5 day

- Conflict resolution 1 day teaching and role play

- Food hygiene certificated learning 1 day

- Lone worker and personal safety training 1 day

- Working with vulnerable adults 1 day

- Refresher e learning materials

- Reflection on critical incidents in the support of application on the CPD file

- Supervision notes which analyse the evidence of application in the CPD file

Overall evaluation

These is ample evidence to demonstrate that the learning outcomes have been met.  There mechanism for ensuring consistency are robust with a high level reporting system for mandatory training.

Quality assurance of training is embedded within the Directorate and Divisional boards with an overarching quality improvement strategy.  Each Division has a designated training lead with an education development strategy group.

Work based learning 1 reablement in practice: 30 credits

Evidence

- Comprehensive record of level 4 competencies

- Reflective witting in CPD file

- Workshops on clinical reasoning 7 days

- Supervisory notes in CPD file

Overall evaluation

There is ample evidence to demonstrate that the learning outcomes have been met.  There mechanism for ensuring consistency are robust.

Recommendations

The assessment strategy for WBL could be changed to a practice based assessment.  Module paperwork has already been forward for approval event.

Action: Jane P to discuss with the School Courses and Approval Team on 24th November

Marking criteria be made clear to students to inform assessment performance.  There are approved generic criteria for a range of assessments in use within the School of Health Studies that will be used with this programme.

Any further action required: Jane.  University of Bradford

Workshop to be provided for work based mentors/supervisors of level 4 support workers to standardise supervision in the workplace.

Action: Jayne & Rachael Calderdale framework

Flow chart to be provided to illustrate quality assurance system for training and development in the Trust.

Action: Bev & Kathy. Training and Development.

APPENDIX 7: POST GRADUATE STUDY DAYS

Blurred Boundaries

Shadowing Report

Jonathan Flynn – Senior Lecturer

University of Huddersfield

School of Human & health Sciences

Queensgate

Huddersfield

HD1 3DH

01484 47920

j.m.flynn@hud.ac.uk

Overview

Following an introductory meeting at Calderdale Royal Hospital a short period of shadowing was established so greater clarity could be gained from some of the teams with regards to training needs.

The following teams were visited:

| Date | Location | Team |
| --- | --- | --- |
| 24.0309 | Allen House | Rehab @ Home |
| 25.03.09 | Huddersfield Royal Infirmary | A& E/ MAU |
| 26.03.09 | Brighouse Health Centre | CRT (Lower Valley) |
| 27.03.09 | Calderdale Royal Hospital | Ward 10 |
| Unable to arrange |  | Macmillan |

It was evident that a degree of work had already been carried out by all teams, with a positive and favourable approach to this style of working.  Currently ‘blurred boundary’ working was identified across the following teams;

| Teams | Professions Involved |
| --- | --- |
| CRT (Lower Valley) | OT/PT |
| CRT (Upper Valley) | OT/PT |
| CRT (Halifax) | OT/PT |
| Rehab at Home (Allan House) | OT/PT |
| Rapid Response Team (Sowerby Bridge) | OT/PT |
| A& E & MAU (HRI) | OT/PT |
| A & E & MAU (CRH) | OT/PT |
| Ward 10 (CRH) | OT/PT/Nurse |
| Palliative Care Team | OT/PT/Nurse |
| OT Assessment Service | Just OT |

Training Requirements

As expected there were different requirements from different locations, below is an overview.

- Using measurement devices such as goniometers to objectively record range of movement.

- Understanding the underpinning knowledge of gait analysis and being able to apply this to the workplace, be it ward, rehabilitation room or patients house.

- Understanding the underpinning knowledge needed for the prescription of walking aids.

- Understanding the underpinning knowledge of exercise prescription and how to practically apply this to the work place.

- Understanding the philosophy and underpinning knowledge associated with the prescription of equipment (bathing, handrails, perching stools etc) and how this can be utilised to assist, focus and contribute towards the patient’s rehabilitation.

- Understanding the underpinning knowledge needed to manage patients with cognition and perception issues.

- Being able to quickly assess mobility, function and cognition in the workplace.

- Taking handovers and assessing which patients should be seen.

- Again equipment with reference to filling in forms, different types of equipment, what can/cannot be given (postcode restriction).

- Referring on – there was a large list of potential areas where patients might be referred onto, this included (outpatient physiotherapy; outpatient occupational therapy;  Barton Centre for neuro, falls and ortho;  community PT and OT; Community Advice and Support Team; community matrons Social Services; Rapid Response; Intermediate Care and  A & E including further x-ray, bloods and urine. Additionally, the potential for unnecessary crossover existed with patients being assessed twice where referrals were made to Calderdale Rapid Response.

- To eliminate where possible unnecessary visits which may be occurring when a therapists is uncomfortable about performing a particular task, which could be easily ‘blurred’ as a competency.

- Understanding the underpinning knowledge associated with wound care, being able to spot there is a problem with a patient’s skin integrity and knowing what to do about it.

- Underpinning knowledge and application of thermal techniques such as hot and cold packs.

- There was a strong feeling for the use of flowcharts (decision charts), which I would suggest, could be made into a handbook to assist/remind staff of the processes.

Concerns

Over the course of the shadowing period a number of concerns emerged.

- The difficulties faced by the teams when making a cross-site referral or request for equipment.

- Knowing exactly what tasks are considered blurred and which are profession specific.

- Remaining autonomous and not being expected to perform these additional tasks as routine, for example placing a patient on a bedpan.  Although useful this type of task may become an expectation by other members of the team and result in other key aspects of rehabilitation being infringed upon.

- Ensuring that contributors and participants are credited both for undergoing the training and for delivering it with their client groups.

- There was strong feeling expressed with regards to understanding one’s limitations and knowing when to refer on.

To Do

For each are (where it has been done already) a decision needs to be made with regards to:

- Which tasks are physiotherapy only

- Which tasks are occupational therapy only

- Which tasks are nursing only

- Which tasks can be blurred into a training package

NB: See appendix 1

Conclusion

There appears to be value with regard to blurred boundary working for both the practitioner and the patient.  A lot of good work has already been done and I would suggest that this is identified, shared and incorporated, as there is little point is re-inventing the wheel, this could be achieved by further steering group meetings.

The Basis of Clinical Exercise Prescription

A two day workshop

Background to the workshop

This course will highlight the background and foundation knowledge needed to prescribe exercise to patients in the clinical environment.  The delivery will be mixed with pre-reading tasks, tutor presented, group practical tasks and discussion throughout the two day workshop.

Who should attend this workshop?

Anyone who needs to know the basic fundamentals of clinical exercise prescription, it is not suitable for experienced staff in this field, it is anticipated that occupational therapists and nursing staff  who are interested in developing this area of their practice would be the likely recipients.

Presented by

Jonathan Flynn – Senior Lecturer

University of Huddersfield

School of Human & health Sciences

Queensgate

Huddersfield

HD1 3DH

01484 47920

j.m.flynn@hud.ac.uk

The Basis of Clinical Exercise Prescription

Summer 2009 (TBC)

| Day 1 |
| --- |
| 09.30 – 09.45 | Registration /plenary |
| 09.45 – 11.00 | Revision of basic exercise physiology & anatomy |
| 11.00 – 11.15 | Break |
| 11.15 – 12.30 | Principles of therapeutic exercise design |
| 12.30 – 13.30 | Lunch |
| 13.30 – 14.00 | Principles of muscle, power, endurance & strength training |
| 14.30 – 14.50 | Break |
| 14.50 – 16.00 | Group task, designing a strengthening regime & feedback |
| 16.00 | Discussion of day one learning material & close |

| Day 2 |
| --- |
| 09.30 – 10.00 | Plenary/questions form previous day |
| 10.00 – 11.15 | Principles of cardiovascular exercise design |
| 11.15 – 11.30 | Break |
| 11.30 – 12.30 | Group task, designing a cardiovascular regime & feedback |
| 12.30 – 13.30 | Lunch |
| 13.30 – 14.00 | Equipment – its use in the clinic & in the home |
| 14.30 – 15.15 | Open question & answer session, putting it all together |
| 15.15 – 15.30 | Break |
| 15.30 – 16.00 | Plenary session/summary |
| 16.00 | Close of course/certificates |

APPENDIX 8: CONSULTATION EVENTS

8a) Support Worker Focus Group – write up

Level 4

What would you need for level 4?

What will it involve that is different to level 3?

- Clients with particular needs ‘trickier’ neurology – doing things beyond competences eg balance work

- Working unpredictability

- Knowledge and awareness resisted to safety

- Assessment - interpret and clinical reasoning

- Broader awareness of holistic context – family, support, dynamics

- What and why?

| Good learning experiences | Less good learning experiences |
| --- | --- |
| Study session | Not sufficiently focused on your job |
| Groups/colleagues | Lack on communication training providers and workplace |
| Off site | Lack of information about what is to be done |
| Full days | Scary – being alone |
| Practical | Too much too soon |
| Written Exam | Not ack. Personal circumstance – tight time frames |
| Certificates nationally |  |
| Shadowing/watching |  |
| Physios encouraged to practise alongside | Acknowledgement - re literacy baseline |
| Involvement | Identify help needed |
| Listening /observation to another more experience on hand guidance | Need for flexibility – adapted to circumstances |
| Relaxed informal not pressurised | Regular contact with person leading |
| Choice of int/ext supervisor/personal tutor | Not being clearly briefed about what is expected |
| Workplace uniformly acknowledgement of process | Clear language need to overcome ‘baggage’ or previous learning need to build confidence |
| Define place and time for assessment |  |
| Reflective accounts |  |
| Portfolio |  |
| KSF – knowledge skills, framework |  |
| Competence framework |  |
| Respiration/assessment |  |
| Piece of paper to evidence it |  |
| Getting back into learning process |  |

Solutions

Optional routes – through according to starting point

Observation by therapist

Workplace/involvement

Access to IT hardware

Interactive workbooks – self directed learning for home working

APEL unit

Designated study group in workplace

- e-learning networking site

- allocated study time (eg 4 hrs per month)

- organisation/understanding of process and needs

Little bite size modules – flexible submission & negotiation structure

IT support needed – writing skills & study skills

Starting point – accredited unit

Knowledge +        Skills

Experience 	Study skills

Clinical reasoning

Assessment certification

Summary of Potential Learners Views

Level 4 Competence

8b) Consultation Event: Certificate of Reablement

October 13th 2009 Escalate Centre, University of Bradford

Attendee: See Appendix

Introduction

A range of stakeholders were invited to attend the event from educational organisations, the University of Huddersfield and Bradford, local NHS Trusts. Calderdale PCT, Calderdale and Huddersfield NHS Foundation Trust, Bradford District Care Trust and  the Strategic Health Authority, NHS Yorkshire and Humberside, Calderdale Council, Skills for Health and Professional AHP bodies.  There were also present, lay representatives and Band 4 Support Workers.

The consultation event began with presentations from Jayne Duffy and Rachael Smith Project Leads for the Calderdale Framework and Jane Priestley, Lecturer, University of Bradford.  These provided the participants with the background to proposed Certificate of Reablement and information about the Calderdale Framework.

Background

The development of a Certificate in Reablement has arisen from an identified need for educational provision for level 4 support worker role with learning outcomes based on job specifications based on National Occupational Standards and Knowledge and Skills Framework.  There is a national acknowledgment of the need to invest in widening participation in life long learning for the support workforce (Skills for Health 2008) and regional support worker education.

In support of the development of the Certificate of Reablement, the University of Bradford can offer:

- Accreditation of in-house training – the Calderdale Framework

- Recognition of prior experiential learning

- Bespoke modules that meet need

- A recognisable transferable qualification

- Progression opportunities within an academic framework

Methodology

A World Café methodology was used with participants being asked to consider the Certificate of Reablement from three different perspectives – learner, educational and organisational.  For each of these, questions were used to stimulate discussion:

Educational perspective

- What key features should be in the programme? ….content

- How should the programme be delivered?  …..methods

- What progression might there be following the programme?

- What other educational activity could be APELed into the programme?

Learner perspective

- What would be the incentive to do the qualification?

- What would be the challenges learners would face?

- What support would be needed?

Organisational perspective

What is the value of the qualifications to Trust?

What are the implications of the programme for Trusts?

How could Trust support students?

Views Expressed

Educational Perspective

The certificate should consist of core modules with optional modules enabling a flexible approach to learning outcomes and meeting the different learning needs of learners entering the programme with varied starting points and experiences. Modules need to demonstrate a clear link to practice, be practical and link where possible to NVQs.  Content recommendations:

- Anatomy and physiology – muscular and respiratory systems

- Communication

- Social Science – understanding individual needs, human interaction, human understanding, psychosocial factors – not solely medical model

- Limits of role in context – understanding boundaries, working within competence, accountability, liability, signposting – facilitating involvement of other practitioners

- Confidentiality, ethics and informed consent

- Clinical reasoning

- Funding systems

- Management of long term conditions and multiple factors

Delivery of the certificate should be in flexible chunks with work based learning as well as formal learning.  The level of teaching should be appropriate to the needs of the learners, with an emphasis on practical training and the assessment of skills within the workplace.  The concept of a skills passport was proposed as a means of recording transferable skills acquired.  The assessment process would require suitability trained assessors and mentors in the workplace from both the social care and health. In relation to this, concern was expressed about a potential capacity issue in the short term.  The user of technology for learning was seen as of value where appropriate - as were creative approaches to learning such as Bradton method, using stimulation exercise with actors and new ways of bringing training into the workplace.

The need for all stakeholders/participating organisations to be involved in agreeing the entry requirement for the programme was recommended as was a proposed timescale for completion being made clear for employers.  It was hoped that the certificate would be a stepping stone to progress on the different levels of work and study.

Learner perspective

It was acknowledged that these were several benefits of the certificate to the learner:

- Potential for carer development with consequent financial record

- Improved skills, knowledge and confidence

- Nationally recognised and transferable qualification

- Improved job satisfaction - better engagement with client/patient with greater continuity of care and a more holistic approach.

- Recognition through APL of previous learning and experience

- First step on escalator – changed perspective to learning – learning how to learn – increased belief in self and empowerment –development of personal desire to develop and progress further.

It was felt that there was a potential risk of disappointment where acquired the certificate did not change banding of role.  It was therefore recommended that learner expectations should be managed and that numbers trained to this level should relate to patient need and be part of the development of skill mix and workforce planning.

Learner retuning to the learning environment may need support to overcome fear of the more technological approaches, e-learning and use of computers generally.  It was proposed that for some such delivery methods be introduced slowly with, where possible, some choice being offered.  At the start of the programme learners needs and preference would need to be assessment and their access to IT provision identified, as well as other practical aspects such as child care and travel costs if attendance away from their place of work was necessary.

There was some discussion about the political implications for the creation of a new tier in the hierarchy and it was important that these should be equity of access to the programme.

Learners would need support within the workplace and from the university.  Within the workplace, managers would need to be appropriately developed and informed to provide necessary support and ensure protected time for study.  Both managers and peers should be aware of the training content and feel included and involved in feedback processes.  Success for the programme would be more likely to be within a supportive organisational culture that valued the learning and gave learners the right to be involved in new decision makers.  Link tutors from the university would be needed as well as systems developed to enable learners to develop their study and IT skills.

It was felt that protected time for learners to study would have financial implications and funded backfill would be required.

Organisational perspective

The value of the certificate and development of the Band 4 role to organisation was identified:

- Knowledge that workforce competent

- Quality assurance

- More flexibility in workforce movement/deployment

- Staff with more holistic view of caring

- Learners learning across boundaries

- Better service provision to the client

- Improved risk management – especially in task delegation

- Good framework to upgadrdae skills

- Enable organisational change

- Career progression – attractive to staff

- Patient centred approach in line with national guidance (Darzi & QCC)

- Enhanced contract with commissioners

- Improved provider reputation

- Improved cost efficiency – financial gain

The establishment of the programme and development of Band 4 roles requires investment and time.  It was suggested that the underutilisation of the SSLF (Support Staff Development Fund) was a potential resource to be tapped.

If roles are to be accommodated there need to be capacity created within the system through an effective needs led service planning process with top level commitment to change.  Such a change will require a commitment to allow flexibility of staff and an acceptance by teams of new skill mix.

To support the change, there will be a need to have qualified staff able to assess and supervise learners and ensure protocols, guidelines and job descriptions are in place with strong links to clinical governance.

Ultimately success if the programme will require ‘sign up’ from the top and a commitment to ensure resources are available to support learners in the form of time, IT support and backfill moneys.

Appendix: Attendees

Louise Johnston	Lecturer (Physiotherapy) & Joint Post Graduate Programme Leader

Division of Physiotherapy & Occupational Therapy

University of Bradford

Nicky Byrne	Macmillan OT and Team Leader

Macmillan Rehabilitation Team

Calderdale & Huddersfield NHS Foundation Trust

Michael Holgate	Lifelong Learning Manager (am only)

NHS Yorkshire and the Humber

Janet Beverley	Allan House Clinical

Calderdale PCT

Alison Headley	Sector Officer (WYLLN)

Health Social Care and Early Years

University of Bradford

Monica Slocombe	Therapy Service Co-ordinator

Long Term Conditions and Rehabilitation

Calderdale & Huddersfield NHS Foundation Trust

Karen Doyle	Reablment Project officer

Calderdale Council

Pat Crossley	Reablement Project Officer

Calderdale Council

Pamela Wood	Apprenticeship Co-ordinator

OD & Training Dept

Calderdale & Huddersfield NHS Foundation Trust

Chris Lamb	Project Manger

Skills for Health

Jak Radice	Learning Resources Mangers and Learning Technologist

TQEG staff member Interactive Learning Centre

University of Bradford

Tabitha Makin	Carer Calderdale

Ian M Wragg	Workforce Modernisation Manager

NHS Yorkshire and the Humber

Fran Labrom	OT Calderdale Reablement Service

Calderdale & Huddersfield NHS Foundation Trust

Ruth Warden	Workforce Information, Performance and Planning Manager

Bradford District Care Trust

Val Rhodes	Workforce Information, Performance and Planning Manager

Bradford District Care Trust

Janette Keane		Band 3 Support Worker

Calderdale & Huddersfield NHS Foundation Trust

Maureen Knight		Band 3 Support Worker

Calderdale & Huddersfield NHS Foundation Trust

Dot Rayner	Membership Council

Calderdale & Huddersfield NHS Foundation Trust

Ibrar Butt	Project Manager WELL (Workforce Engagement in Lifelong Learning) Project

University of Bradford

Vicki Illingworth	Learning Support Officer, Escalate Centre, University of Bradford

Apologies received from;

Jackie Turnpenney	AHP Lead Greater Manchester and Cheshire Cancer network

Debbie Graham 	Assistant Director – Innovation & Development

Calderdale PCT HQ

Sara Eastburn	University of Huddersfield

Catherine Carus	University lecturer and Admissions Tutor, Division of Physiotherapy and Occupational Therapy, University of Bradford

Anne Jackson 	Commissioning Manager Physical and Sensory Impairment, Adults, Health and Social Care

8C) Calderdale & Huddersfield NHS Foundation Trust Membership Council

Some of our questions;

Will this new training and new skills be recognised?

Yes, at Band 3 the competencies are APEL to NVQs and the band 4 will undertake a certificate in reablement (120 credits)

Who trains the trainers?

This will be addressed via the steering groups.  Currently qualified staff who are responsible for students undertake training to become clinical educators.

What do the professional bodies think?

We will let you know the outcomes from the consultation event.  The CSP and COT are keen to develop support staff.

How are the universities involved?

Bradford University are supporting the level and initiative.  Huddersfield University are supporting the level entry initiative.

What are the links to NVQs?

Hopefully this has been addressed in the first point.

How does this work in PCTs?

Rapid Response use this model but here is work to do to make this more robust.  The Commissioner for Cancer Services at Calderdale PCT was invited to attend the project reference group and has all the minutes.

Has it meant recruiting more people to fill the ‘gaps’?

Yes and no.  By sharing skills you get better use of staff in time this may mean more band 4 (assistant practitioners) are recruited or developed from the current workforce.

What are the benefits to the patients?

Improved access to services and makes sure people who need specialist interventions get them.  Sharing skills means patients see fewer faces and don’t have to report their story unnecessarily.

How do we ensure that the service isn’t diluted?

By implementing a standardised training approach.

Are there systems in place to monitor this approach?

Yes, clinical supervision is well established as is regular audit of practices, complaints, compliments and clinical incidents.

How are you capturing user/patient feedback?

By consulting with you in the first place.  Ongoing patient feedback is sought across the services.  Your suggestion of a case study scenario will be followed up on 20th October with Dot Rayner. Dot has kindly agreed to attend the consultation event with Bradford University on 13th October (thanks very much)

How can we make this work seamlessly across: 1 x Acute Trust, 2 x PCT Trusts, Social Services?

This question will be taken to our steering group for senior managers to follow up.  We will keep you posted.

8d) Case Study  - A patient with Rheumatoid Arthritis

- August - GP made preliminary diagnosis of polyarthritis; referred to Consultant Rheumatologist

- September – Consultant Rheumatologist diagnosed RA; drug therapy begun

- October – RA not responding to treatment; extreme pain and stiffness; difficulty with daily tasks and personal care.  Asked rheumatology burse practitioner for physio help (how to make best of limited range of movement, exercise to increase flexibility etc) referrer to Rehab at Home team(OT & Physio)

- December – joint home visit by OT & Physio; examination and practical discussion.  Further (separate) appointments made for Physio treatment and OT support, referrer for Podiatry home visit.

Because of long-standing OA and personal knowledge/experience, had already made some adjustments (wearing stretchy clothes without zips/buttons, reorganising kitchen and bedroom storage, using portable step to minimise reaching, using easy-grip pens, kitchen utensils etc) but bathing personal care difficult.

OT ordered bath board from stores (2-3 wks delivery) but fractionally too short for bath and felt wobbly so bath seat ordered instead (2wks delivery).  However, bath has curved base so seat didn’t fit; offered an electric bath lift which I declined due to impact on others using the bath (removable but too awkward for me to manage, especially on a daily basis).  Offered to order a toilet frame but I was managing just using natural supports.  At 6th (last) visit, gave me a dressing stick.

Physio suggested wrist splints, but as these are supplied by the hospital I had to wait until next rheumatology appointment and ask for them (but they were then supplied immediately) NB perhaps because of the handover between physio and nurse, I was unaware that I should not wear them too much, to avoid risk of bones fusing - this only came to light 3 months later during a general discussion at a follow up visit.  Physio said she’d like me to try a wax hand bath but as they were not available in Calderdale (although they are in Huddersfield) suggested using bowls of hot water.  However, this was impractical due to difficulty in carrying things (husband unable to help due to illness).  At 5th visit, suggested trying acupuncture at next visit; agreed but at the hospital appt. a few days later I was given a steroid injection and was thus not able to have acupuncture at the last 6th (last) physio visit.

Podiatrist felt that specialist rheumatology podiatry was required but it would be better to wait until new treatment has stabilised RA slightly.

3rd Feb - referred to rheumatology podiatrist but appt (17April) was with general Podiatrist.

Orthotic insoles ordered (approx 6wks delivery quoted it actually took 10 weeks)

6th Oct – follow up appt; orthotics not quite right; new ones ordered (approx 8wks delivery quoted but actually took over 3 months – rec’d mid Jan)

Summary of meeting with the patient

Please note this person wishes to be referred to as the patient.

Please refer to patient’s case study and note below key points arising in relation to Calderdale Framework (Roles for Assistant Practitioner Blurred Boundary worker)

Joint visit by OT and PT and subsequent separate visits: Patient felt this could have been addresses by one, trained therapist who had an overview of current need and a longer view of the future.

This would have been welcomed as in an acutely ill phase at time of multiple visits sometimes on same day.

Referrals onto other services and subsequent visits for interventions eg orthotics and podiatry could have been minimised, again leading looking at skill set of therapist in the community team.

Practitioners in other services could also be skilled up eg nurses to address splints.

Comments arising from patient’s perspective;

- Validation of this practice is essential to the training underpinning these roles need to be robust.

- Monitoring systems also need to be in place to ensure quality assurance for patients

At the end of this is communication between and with patients and ll involved in their care.

NOTE: The patient feels that this ‘story sharing’ experience has been to articulate her story and not to complain.

Other issues arising to feedback:

- Lack of information at initial diagnosis? Role for assistant practitioner

- Social support (as and when needed not made aware of this

- Access to equipment should be dependent on need and not availability provisions of equipment should be timely and accurate

- Case management approach of patient was not felt to be apparent ‘Communication between professionals needs to be more integrated’

- Has got self re-referral but unaware to which bits of service and how long does this last for?  And as a consequence is buying her shoes from the internet.

Having discussed the above with this patient we have asked if we can submit a C17 patient and public involvement form (patient agreed) and then feedback the outcome of this process.

Health Care Commission – Draft Criteria for Assessing Core Standards in Provider Organisations (Annual Health Check 2008/09)

C17 Patient & Public Involvement

Division: Medicine & Elderly Date: 23/10/2009

Directorate: Clinical Therapy & Rehabilitation

Lead person: Jayne Duffy & Rachael Smith

Contact Details: 01422 305570 jayne.duffy@cht.nhs.uk or rachael.smith@cht.nhs.uk

What was the PPI activity? To consult service user on project of new ways of working (skills for health sponsored) and the Calderdale Framework.

What were the objectives for the activity? To consider patient experience and how application of new ways of working could improve this (if at all)

Please give relevant details and attach evidence Please see case study (provided by service user) and summary of story told by service user with reference to benefit of new ways of working

Which line of enquiry would this sit, element 3 or 27

What follow up action do you plan as a result of this event? ie feedback to those involved Feedback to team service user dealt with including report to SFH a patients perception of benefit on new ways of working

## REFERENCES

## College of Occupational Therapists 2004, A National Framework for Support Worker Education and Development, COT, London.

## Department of Health 2005, The National Service Framework for long term conditions, HMSO, London.

## Department of Health 2008a, A high quality workforce: NHS next stage review.

## Department of Health 2008b, Framing the contribution of allied health professionals - delivering high quality healthcare, HMSO, London.

## Department of Health 2008c, Modernising allied health (AHP) careers, HMSO, London.

## Department of Health 2008d, Modernising allied health professions (AHP) careers: A competence based career framework, HMSO, London.

## Department of Health. The health and social care act.  2008e. London, HMSO. 
Ref Type: Statute

## Lord Darzi 2008, High quality care for all: NHS next stage review final report.

## Lord Leitch 2006, UK Skills: Prosperity for all in the global economy – world class skills, HMSO, London.

NHS Modernisation Agency 2004, Changing Workforce Programme: developing support worker roles in rehabilitation and intermediate care services.

## Skills for Health 2006, Sector skills agreement for health executive summary (England): Delivering a flexible workforce to support better healthcare and healthcare services, Skills for Health, Bristol.

Skills for Health 2009, Core Standards for Assistant Practitioners

Smith R & Duffy J 2008 www.healthcareworkforce.nhs.uk/ffc

Smith R & Duffy J 2009, Developing a Competent & Flexible Workforce in Rehabilitation using The Calderdale Framework (submitted for publication)

## Wanless, D. 2004, Securing good health for the whole population, Department of Health, London.

uHHH

# Footnotes

E.g. National Reference Group

# Text boxes

| Objective/Product | Final Outcome | Benefit | Benefit Evidence | When will benefit be take effect | When will benefit realised |
| --- | --- | --- | --- | --- | --- |
| 1To define the Team competences and profile based on patient needs for the MacMillan Rehab team and Early orthopaedic discharge team. 2. To identify generic competences to be used in an MDT & Identify the defined competences that currently remain in a specialised profession. 3. To develop a competence cluster for new roles at Level 4. 4.To identify the educational requirements needed to underpin these new ways of working and new roles. | 1. To create competence based job descriptions based on patient need. 1. To begin to reshape the orthopaedic early discharge team and to inform the future structure of the MacMillan Rehab Team 2. To inform production and generation of competency training pack for each of the new roles. 2,3,4. To facilitate career progression through the AHP career framework by removing artificial barriers through validation of individuals competence | 1.Improved effectiveness & efficiency of service provision for the patient 1.Additional stages on the career framework to take people from level 2 to level 6/level 7/8 2. Quality assurance, risk management, consistency of approach & service delivery 1,2,3,4 Improved staff satisfaction, including confidence in own role competence. 1,2,3,4 Reduced complaints and increased compliments and overall patient satisfaction 1,2,3,4. To contribute to Cancer Action Network Project 4.Improved access to education and qualification | 1. reduced cost per contact. Increased throughput 1,2,3,4.Staff satisfaction survey and questionnaires 2. Data on complaints and compliments. Patient satisfaction questionnaires 1,2,3,4 Staff satisfaction questionnaires | 1. Some data by Oct 2009 “ 2. Some data by Oct 2009 against current baselines 1,2,3,4: Oct 2009 4.Short term (Oct 2009) & ongoing : enrolments | Longitudinal study 2010 onwards against current baselines Ongoing – yearly data collection Repeated every Sept 4. Long term (2010 onwards): qualifications. |

1

Awareness Raising

2

Service Analysis

3

Task

Analysis

4

Competency Identification

5

Supporting

Systems

6

Training

7

Sustaining

7 Stages to

Successful Implementation

| Core Personal & Professional Development 1 Evaluates practice Participated in supervision of self & others Training responsibility for self & others 20 | Core Tools & Techniques for Work Based Study Functional Skills Study skills Use of work based protocols Critical appraisal skills 20 |  |
| --- | --- | --- |
| Core Workplace in context 1 In depth knowledge of role & limitations Legal & ethical issues Awareness of wider health/social care issues 20 | 60 credits taken from optional modules: Learning from experience in the workplace: Acquisition of specialist clinical skills for example assessment for equipment & therapeutic interventions 9competencies)- double module (40) Reflections on professional study (20) |

Plans straightforward tasks and works guided by standard operating procedures and protocols

Works to agreed protocols

Exercises a degree of autonomy depending upon the complexity and risk of procedures being undertaken

Prioritises own workload

May be responsible for planned, delegated care

Undertakes well defined tasks requiring limited judgement

Demonstrates self-directed development and practice

Assistant Practitioner

Process Knowledge

Personal and Professional

Contextual Knowledge

Delegates to others

May supervise others

Evaluates practice and suggests changes to improve patient care

Undertakes the ongoing supervision of the routine work of others

Takes some responsibility for the training of others and may deliver training

May have specialist clinical skills e.g.

- Spirometry

- Female catheterisation

- Monitoring long term conditions

- Continence advice and referral

- Assessment for equipment and therapeutic interventions

- Injections

High degrees of technical proficiency

Makes judgements requiring a comparison of options

In depth knowledge of role

May include cross professional knowledge

Legal and ethical

Aware of wider healthcare issues

Leadership

Skills for Health

Level 4 Certificate HE

IT demo of poss.  Study techniques

Intro – route/structure/support

Bite size Units

Reflective skills

Study skills

New roles

Optional specifics

Curriculum design

Identify gaps

Accreditation

Calderdale

Competency

Framework

What’s available already?

Chat room group

APEL Experience

Organise Support

IT study skills

Mentors

120 pts certificate in therapeutic practice

Portfolios

Int workbooks

E learning

Group Study day

Assessment method